## Complaints
HumeLink West Joint Venture Complaints Register
Year | Month | Date | Time received | Number of complaints | How complaint was received | Local Governent Area | Topics raised | Avoidable/ unavoidable | Summary | Responses and investigation | Salesforce ID | Oustanding actions | Status | Date closed
2024 | November |  |  | No complaints registered
2024 | December | 2024-12-03 | 11:18AM | 1 | SMS | Wagga Wagga | Traffic and Transport | Unavoidable | Temporary traffic management controls (including signs and traffic lights) required for worker safety during road survey work causing delays, and obstructing heavy vehicle turning circle and line of sight when exiting and entering driveway. | Motorists cannot be delayed at temporary traffic lights for more than three minutes and most vehicles are held for less than three minutes to allow traffic through the work area. Traffic control setup was assessed as compliant to the approved traffic management plan. The temporary traffic controls were repositioned to facilitate a wider turning area for a heavy vehicle and allow for longer line of site for vehicles entering or exiting the driveway. The traffic management plan and actions taken were discussed with the stakeholder and the project team working along the road will ensure all efforts will be made to minimise delays, including traffic controllers in place to assist residents and motorists. | ACT-89702 | Nil | Closed | 2024-12-04
2024 | December | 2024-12-02 | 01:00PM | 1 | Phone call in | Wagga Wagga | Property access | Avoidable | Stakeholder reported that project team had accessed private property without notification. | Stakeholder was advised that project representative was being escorted on adjacent land and was unaware they had crossed over the property boundary into the stakeholder's property. Project teams will refer more carefully to boundary maps and not rely on escorts to ensure no unauthorised access. | ACT-89496 | Nil | Closed | 2024-12-19
2024 | December | 2024-12-09 | 08:32AM | 1 | Phone call in | Wagga Wagga | Property access | Avoidable | Stakeholder reported an internal property gate was not locked in the same position following access by the project team. | Variances in pre- and post- gate access photos were identified and alternative lock mechanisms were discussed with the stakeholder. Briefing on the specific gate lock mechanism will be provided to the project teams prior to access. | ACT-89316 | Nil | Closed | 2024-12-09
2025 | January |  |  | No complaints registered
2025 | February | 2025-02-10 | 10:59AM | 1 | Email | Wagga Wagga | Safety | Unavoidable | Stakeholder concerned with worker safety, specifically non project-related dust impacts to construction workers. | Dusty conditions are prevalent due to dry and windy weather, and non-project related vehicles passing at speed. Provided stakeholder with information on current and planned dust mitigations implemented by project team, in consultation with Wagga Wagga City Council. | ACT-93556 | Nil | Closed | 2025-02-10
2025 | February | 2025-02-10 | 08:54PM | 1 | Email | Snowy Valleys | Visual Impact Construction methodology Project engagement and communications | Unavoidable | Community member concerned about the visual impacts from their property, potential impacts to property value and project communication received. | Complaint acknowledged and investigated. Detailed response provided and site visit undertaken. Ongoing engagemet with resident underway. | ACT-93683 | Ongoing engagement | Closed | 2025-02-27
2025 | February | 2025-02-18 | 1:04PM | 1 | Phone call in | Wagga Wagga | Construction - Traffic | Unavoidable | Stakeholder concerned with large amount of traffic control resources in operation. | Temporary traffic management is implemented in accordance with approved traffic management plans and standard traffic procedures in compliance with the Transport for NSW Traffic Control at Work Sites Technical Manual. | ACT-94115 | Nil | Closed | 2025-02-18
2025 | March | 2025-03-03 | 3:08PM | 1 | Email | Wagga Wagga | Safety | Unavoidable | Stakeholder concerned with worker safety, specifically non project-related dust impacts to construction workers. | Provided stakeholder with information on current and upcoming work activities and planned mitigation measures. | ACT-95429 | Nil | Closed | 2025-03-10
2025 | March | 2025-03-03 | 04:03PM | 1 | Meeting | Snowy Valleys | Safety | Unavoidable | Concerned with road safety in relation to project vehicles in the vicinity of school bus drop off/pick up location. | Contacted stakeholder to advise the bus company has been contacted for more information, and the project team has been toolboxed on road safety pertaining to school buses in the area. | ACT-95705 | Discuss options to improve safety with Snowy Valleys Council | Closed | 2025-03-31
2025 | March | 2025-03-19 | 11:38AM | 1 | Phone call in | Wagga Wagga | Property access | Avoidable | Resident reported members of the construction team on his property without notice. | Complaint acknowledged and stakeholder advised that the current process will be investigated and changes made to avoid a repeat incident. An interim procedure of signage installed to indicate permitted access points is being instituted while a review of current digital wayfinding procedures is underway. | ACT-96994 | Nil | Closed | 2025-03-21
2025 | March | 2025-03-21 | 09:19PM | 1 | Email | Wagga Wagga | Dust | Unavoidable | Mitigation measures in place are not sufficient to remedy dust impacts when works are finished. Request to seal Livingstone Gully Road. | Complaint acknowledged and information on mitigation measures provided to the stakeholder, including upcoming road rectification work, reduced vehicle speeds and regular application of water for dust suppression. Dust levels have been monitored and assessed as compliant with the project conditions of approval. | ACT-97278 | Nil | Closed | 2025-03-24
2025 | April | 2025-04-16 | 4.53PM | 1 | Phone call in | Wagga Wagga | Construction - Traffic | Avoidable | Concerned about road sign indicating motorists should slow down. | Stakeholder contacted to confirm receipt of complaint and seek more details of the incident. Further investigation found that one eastbound variable message sign was displaying an incorrect message for motorists when there was no roadwork taking place. The sign information has rectified and is providing correct information. | ACT-99976 | NIl | Closed | 2025-04-17
2025 | April | 2025-04-22 | 11:26AM | 1 | SMS | Wagga Wagga | Noise | Unavoidable | Traffic control setup has trucks braking near property with subsequent noise impacts | Traffic control setup adjusted to reduce noise impacts. | ACT-100196 | Nil | Closed | 2025-04-22
2025 | April | 2025-04-28 | 7:39AM | 1 | Email | Snowy Valleys | Visual Impact | Unavoidable | Resident concerned about visual impact from their property following up on site visit and detailed outcomes of visual impact assessment in their area | Ongoing engagement and project progress updates. Site visit with visual impact consultant pending to be confirmed and undertaken over the next couple of weeks. | ACT-100400 | Coordinate site visit | Open
2025 | May | 2025-05-05 | 8:52AM | 1 | SMS | Wagga Wagga | Dust | Unavoidable | Dust from the construction site is interfering with asthma and washing is getting dirty. | Met with stakeholder and confirmed impacts have abated. Advised two water carts are operating at the site to reduce dust, and work is stoppped while water trucks are refilled. Current work activity to strip topsoil will be completed in coming days. | ACT-101490 | Nil | Closed | 2025-05-05
2025 | May | 2025-05-06 | 2:41PM | 1 | Phone call in | Wagga Wagga | Dust | Unavoidable | Dust from the construction site as no water is on site | Provided stakeholder with information on current and upcoming work activities and dust suppression measures including: - two water carts in operation at the site and works stopped while water carts are filled - three semi-trailer water tankers on rotation to keep water carts filled - running machines at a slower speed to minimise soil disturbance - works stopped periodically to allow dust to settle - ongoing dust monitoring to ensure no exceedances - soaking stockpiles - adding soilbinder when stockpiles are static Contributing factors to dust include: - unseasonably dry and drought conditions - topsoil composition | ACT-101631 | Nil | Closed | 2024-05-06
2025 | May | 2025-05-09 | 08:52AM | 1 | SMS | Wagga Wagga | Dust Noise | Unavoidable | Dust and noise from the construction site | Advised stakeholder that dust and noise levels are being monitored and within approved levels. Weekly update meeting scheduled to discuss upcoming works and mitigations specific to the receiver. | ACT-102316 | Meeting organised with stakeholder to discuss on construction activities and mitigation measures in place | Closed | 2025-05-13
2025 | May | 2025-05-13 | 11:29AM | 1 | Website | Wagga Wagga | Safety | Unavoidable | Concerned that proposed temporary hard road barriers will be dangerous as kangaroos will be trapped within the road corridor. | This issue will be considered in the planning of traffic management to ensure road user safety. | ACT-102510 | Nil | Closed | 2025-05-13
2025 | May | 2025-05-14 | 07:28AM | 1 | SMS | Wagga Wagga | Traffic and Transport | Unavoidable | Project vehicles accessing restricted area of Mates Gully Road with potential property damage. | The vehicles observed were identified as not related to the project. Stakeholder provided with contact details of business responsible for identified vehicles. | ACT-102589 | Nil | Closed | 2025-05-14
2025 | May | 2025-05-14 | 08:02PM | 12 | Website | Wagga Wagga | Environment - Cultural Heritage Construction - Noise and vibration Construction - Traffic Construction - Dust Traffic and Transport Engagement/Notification – Near Neighbour Engagement | Unavoidable | Concerns with project vehicle usage/parking on Mates Gully Road, noise and dust, water usage, cultural artefacts, consultation, and current and proposed traffic management controls on Mates Gully Road. | A detailed response was provided to the stakeholder, addressing the issues raised. | ACT-102675 | Nil | Closed | 2025-05-20
2025 | May | 2025-05-17 | 12:38PM | 1 | Phone call in | Wagga Wagga | Dust | Avoidable | Concerns with dust on the construction site. | No works are currently in operation, but windy conditions are disturbing the recently excavated topsoil. Water carts will be sent to the site to water down the area and water carts will continue to operate during standard construction hours. | ACT-102979 | Nil | Closed | 2025-05-17
2025 | May | 2025-05-17 | 1:15pm | 1 | Phone call in | Snowy Valleys | Property access | Under investigation | Stakeholder reported that project team had accessed private property without notification. |  | ACT-102945 |  | Open
2025 | May | 2025-05-30 | 1:04pm | 1 | Phone call in | Snowy Valleys | Social License - Negative impact | Unavoidable | Concerns with project vehicles collecting potable water at Memorial Avenue, Batlow and leaving none for community. | Records show no potable water has been collected by the project at this location to date. | ACT-104687 | Nil | Closed | 2025-05-30