## PECe
Project EnergyConnect (Eastern Section) Complaints Register
Year | Month | Number of Complaints | Date | Time received | How complaint was received | LGA | Topics raised | Avoidable / unavoidable | Summary | Investigation and response mitigations | Salesforce ID | Outstanding actions | Salesforce ID | Status | Date Closed
2023 | March | 1 |  |  | Telephone |  | Traffic Management |  | Long delays and disruption to local traffic | Complaints investigated. Traffic control looking at ways to reduce delays for local traffic. Some small adjustments have been made to the programming of the traffic lights that do not compromise worker or public safety. Resident contacted by phone to explain traffic management process and offered face to face meeting. |  |  |  | Closed
2023 | April | No complaints registered to date |  |  | N/A
2023 | May | No complaints registered to date |  |  | N/A
2023 | June | No complaints registered to date |  |  | N/A
2023 | July | No complaints registered to date |  |  | N/A
2023 | August | No complaints registered to date |  |  | N/A
2023 | September | 3 |  |  | Email from Arch Services on behalf of complainant. |  | Use of Channel 14 on radio |  | At first the complaint was regarding bad language being used by contractors on channel 40. After phone calls by both Transgrid and SecureEnergy it was realised that the complaint was more about the use of Channel 14 - a common channel used by local farmers in Lockhart. The complainant wanted SecureEnergy to cease using any channels between 1 and 30. | Complaint investigated. SecureEnergy does not use Channel 40 at all. We do however use Channels 14, 15 and 17 in the local area. Discussions with the Construction Team regarding radio etiquette on any channel and this is being reinforced in daily prestarts. Still discussing with the Construction Team about using Channels 30-40 instead. Our Land and Property Access Manager is also contacting some of our landholders in the area to see what channel is not often used by the farmers. Our Construction Delivery Manager has agreed to change Channel 14 to a less used channel. Currently investigating options. TG have been in contact with complainant to outline actions. SEJV have contacted several landholders to discuss the use of Channel 14, the general reply regarding the UHF use was that providing the radio is used professionally for short discussions there should be no complaints. Investigating radio protocols and site notice will go out to all staff outlining protocols for use of radios. |  |  |  | Closed
2023 | September |  |  |  | Telephone from landholder |  | Gates left open |  | Landholder is angry that site crews failed to close two gates on his property with one being a property gate. | Complaint investigated using IVMS data from vehicles. The last contractor to access his property was completing geotechnical testing. The data showed both vehicles involved stopped for an extended period at the time at the property boundary and between properties indicating they would be opening and closing gates in that time frame. We are still awaiting two more subcontractor IVMS records to show their movements on the day. We have again reiterated the closing of gates in prestarts. SEJV have provided updates to the landholder. Landholder providing quote of damage to cattle. |  |  |  | Closed
2023 | September |  |  |  | Telephone from landholder |  | A subcontractor driving a low loader along Hanging Rock Road speeding whilst negotiating a bend. |  | Landholder very concerned and considered this a near miss. The landholder was very upset by this near miss as a similar incident occurred in the past killing someone close to her. | The landholder has been contacted numerous times to update her on our actions. The incident has been raised with the SecureEnergy Project Manager who has reported the incident to the subcontractors management. Currently we are awaiting feedback from him on the actions they will put in place to address the complaint and what they will do to ensure their staff attend to the speed restrictions along this road. Investigating reducing the speed limit on Boiling Down Road for all project vehicle movements. Driver in question has been reprimanded for the incident. |  |  |  | Closed
2023 | October | No complaints registered |  |  | N/A
2023 | November | 2 |  |  | Verbal advice to onsite crews. Email from landholder (lessee) lawyers on H 195 to Transgrid on 24 November 2023. |  | Project equipment required to enter property not presented in a manner of satisfactory cleanness for the approval by the landholder to enter the property. Machinery was inspected off the project alignment and had not entered the property. The inspection process was part of the Property Management Plan and Biosecurity Plan conditions. |  | Landholder concerned the vegetable matter and soil on the equipment could fall from the machine whilst travelling through the property and may introduce unwanted species of weeds & grasses onto the property. | Equipment did not enter the property and was returned to the Elecnor Australia yard for additional cleaning. No attempt to access the property after additional cleaning of the equipment was made. For noting actions include: • Internal meetings to review landholder Property Management Plan. • New Induction created for access onto property for all Construction and Subcontractors. |  |  |  | Closed
2023 | November |  |  |  | Email from local resident. |  | Environmental complaint relating to clearing of large trees at Brookong State Forest. |  | The complainant has criticized the loss of big trees that have been felled in the Brookong Forest near Lockhart and wants to know why this forest has been chosen as a as a location for the infrastructure project. The complainant also states they have experienced emotional distress as a result of our actions and is want to know what compensation if any, is available. | Transgrid has responded to the Complainant by explaining the selection process for the EnergyConnect corridor. The vegetation clearing at Brookong State Forest is also in line with all relevant environmental approvals for the project as well as the mitigation measures in place to minimise impact to fauna in the area. Finally, to the second part of the complaint, Transgrid does not offer personal compensation n for emotional distress associated with clearing within Brookong State Forest. |  |  |  | Closed
2023 | December | 2 |  |  | Letter from a landholder's solicitor. |  | Landholder complaint relating to biosecurity protocols not being followed as part of an ongoing complaint, first raised in September 2023. |  | The complainant found an excavator covered in foreign plant matter and soil found on his property, raising concerns about biosecurity. | The project team are investigating current procedures and identifying where improvements can be made with regards to ensuring appropriate processes are followed. Internal investigations indicated greater care to be taken when cleaning plant and equipment. Additional training for Project operators regarding plant clean down procedures have been performed at the Lockhart wash down facility. |  |  |  | Closed
2023 | December |  |  |  | Verbal advice |  | Landholder conveyed dissatisfaction over the arrival of a construction grader on his property without prior notification. This occurred during harvest. |  | The landholder's harvesting operation was impeded by construction activities, resulting the landholder standing down. | Investigations into the incident and discussions with the landholder to resolve the issue have occurred. The investigation indicated the possible factors that contributed to the incident were: Inadequate communications Expediting daily productions insufficient scrutiny by Land Access Team and lack of briefing during hand over of supervision roles. These matters have been attended internally through personal discussions between Supervisors and Managers, pre start meetings and review of Project section inductions. |  |  |  | Closed
2024 | January | 1 |  |  | Verbal advice |  | Landholder H-188 conveyed frustration at not being notified about construction works on property. He noted that he had no point of contact on the project. | Avoidable | Landholder wanted to spray weeds and spread lime. | The landholder was informed that Transgrid and Elecnor Australia have the right to access the property and have provided formal written notification as to construction activities. The landholder was also notified that the Land and Property Access Manager was still his point of contact for all Land Access Issues. |  |  |  | Closed
2024 | February | 1 |  |  | Email |  | RAP member not happy with not being informed of the breach of Wiradjuri Cultural Heritage. | Avoidable | Some unauthorised clearing of access track near structure 131. The clearing occurred prior to surface collection or an exclusion fence being installed. The isolated artefact can no longer be located. | The ACHAR was reviewed and found the artefact in question was listed for potential destruction. Under the EIS conditions, the project is not required to inform RAPs of non-compliance or incidents. NSW DCCEEW are being notified of the breach. The RAP in question has been contacted and email acknowledged. The RAP was again contacted and advised on 1 February that RAPs were invited to attend the site the day after the incident. The invitation continued for several days after. Several RAPs did attend during this period. The RAP sent a letter on the 4th of February outlining his dissatisfaction with internal systems and processes. |  |  |  | Closed
2024 | February | 1 |  |  | Email |  | Another RAP member dissatisfied with the possible breach related to previous complaint. | Unavoidable | Some unauthorised clearing of access track near structure 131. The clearing occurred prior to surface collection or an exclusion fence being installed. The isolated artefact can no longer be located. | RAP has requested a meeting to discuss issue. 16/2 - EA's Environmental Approvals Manager planning to meet RAP member 22 or 23 Feb to discuss issue. Issue subsequently escalated to TG - Proponent will now manage issue direct with RAPs. |  |  |  | Closed
2024 | February | 1 |  |  | Email |  | Another RAP member was dissatisfied with not being informed of the breach of Wiradjuri Cultural Heritage. | Avoidable | Some unauthorised clearing of access track near structure 131. The clearing occurred prior to surface collection or an exclusion fence being installed. The isolated artefact can no longer be located. | RAP has requested a meeting to discuss issue.16/2 - EA's Environmental Approvals Manager planning to meet RAP member 22 or 23 Feb to discuss issue. Issue subsequently escalated to TG - Proponent will now manage issue direct with RAPs. |  |  |  | Closed
2024 | February | 1 |  |  | In person |  | The driver (and passenger) of a white panel van heading south along the Kidman Way at Bundure NSW, claim a rock from a truck heading north from the Dinawan substation hit and damaged their van. | Avoidable | A member of the public drove into Dinawan Substation 2 site at 1.40pm today (Friday 16 February 2024) and stated they believed a rock from a truck leaving the substation had hit their white panel van. They produced a rock weighing approximately 1kg or a bit less. | The driver of the van asked to contact Elecnor Australia with more details about the incident. The health and Safety Team have taken action by re-iterating vehicle exit protocols to sub-contractors and increasing the visual inspection frequency of the road adjacent to the camp access point to identify loose debris. 19/2 - contacted community member again, asking for written details of the truck. Senior Change and Risk Manager is now investigating sub-contractor policies to facilitate the insurance claim process if required. Will update the register when community member supplies further detail, and initiate the claims process if details verified and sub-contractor confirmed. Any further correspondence with the community member will be updated in Salesforce. |  |  |  | Closed
2024 | February | 1 |  |  | Email |  | Landholder dissatisfied with Transgrid Land Access Team Member understanding of Property Management Plan requirements on property. | Unavoidable | Meeting held on 22 February with TG and Elecnor Australia personnel. H189 Landholder has raised dissatisfaction with TG representatives understanding of the Property Management Plan for that property. Landholder also took offense to aggressive manner TG representative showed to Elecnor Australia representatives. Landholder has requested TG representative not attend any future meetings with them . | Complaint raised with TG, Awaiting investigation and outcomes. TG Investigated complaint. The landholder has been contacted by TG on 26 February 2024. The summary outcome from this conversation was that Elecnor land access officers are the primary point of contact – should there be a requirement for Transgrid representation at future meetings, an alternate appropriate representative will attend. The landholder was satisfied with the response. |  |  | ACT-58153 | Closed
2024 | February | 1 |  |  | In person |  | Landholder expressed dissatisfaction with the state of his property following enabling works. | Avoidable | As a result of clearing and grubbing works, the landholder submitted a quote to Elecnor to do his own remediation works. | Elecnor Australia will use their own equipment to carry out the remediation works. Elecnor to organise a date with the landholder for these works to occur. |  |  |  | Closed
2024 | February | 1 |  |  | Phone |  | Concerns about vehicles exiting a property that has no off easement access. | Avoidable | Landholder observed heritage vehicles exiting his property past his sheds even though this property has a no off easement access requirement. The landholder was concerned that if property were to go missing from his sheds, the finger could be pointed at these workers who were at risk by travelling off the easement. | Workers have been advised to only use the easement. No entry signs and shut the gate signage has now been installed on the property as of 4 March 2024. |  |  |  | Closed
2024 | 2024-03-16 | 1 |  |  | Email |  | RAP member disappointed with the potential breach of Wiradjuri Cultural Heritage at Pad 29. |  | RAP seeking clarification from EA Enviromental Manager and expressed disappointment at the prospect of grading work taking place on a roadway yet to be surveyed for Wiradjuri cultural items. | The matter is currently being investigated by the Enviromental Manager. TG Enviromental Manager has been notified and will manage the communication with RAP. |  |  |  | Closed
2024 | 2024-03-16 | 1 |  |  | Phone call |  | Landholder made a complaint to EA Land and Access Officer that he has not received payment for crop damage which he claimed to Transgrid in December 2023. | Unavoidable | Landholder made a complaint to EA Land Access Officer on Friday 15th March in the evening via phone call saying he has not received a compensation payment for crop damage which he claimed to Transgrid in December 2023. He is requesting that someone from Transgrid respond to his complaint. | The matter has been referred to Land and Access Manager at Transgrid for follow-up. |  |  |  | Closed
2024 | 2024-03-18 | 1 |  |  | Email |  | Another RAP member has expressed dissatisfaction with the potential breach of Wiradjuri Cultural Heritage. | Avoidable | RAP expressed disappointment upon receiving a communication from a fellow RAP regarding the potential breach of Wiradjuri Cultural Heritage. The RAP is seeking a meeting with Secure Energy (Elecnor). | TG Environmental and Sustainability Manager has been notified and is coordinating a communication response and meeting with the RAP. |  |  |  | Closed
2024 | 2024-03-20 | 1 |  |  | Verbal |  | Gate left open on L/H H044 Line 2 West and cattle wondered from property. | Avoidable | Landholder lodged a complaint after construction crew left gate open and cattle wondered on Stuart Highway. LJ has now placed a lock on access gate denying activities on the property. | Land Access Officer meeting with LH today to discuss matter at Balarand and investigating issue. Mitigation measures to be reported following the meeting. 21/3 - Expenditure has been approved for additional security cameras at PEC access gates. Land Access Team arranging another campaign and handout materials at prestart meetings to again alert the crews to the dangers of not closing gates |  |  | ACT-60849 | Closed
2024 | 2024-03-21 | 1 |  |  | Email |  | Resident is concerned about damage to the Brookong State Forest at Lockhart following transmission tower pad sites and towers being constructed. | Unavoidable | Resident spoke in person to an Elecnor Australia representative on Sunday 18 February 2024 about their concerns in relation to the Brookong State Forest and what legacy will be left for Lockhart Shire once the towers are built. The resident followed this up with an email sent yesterday (20 March) to an incorrect email address and received today (21 March) about the matter. | A response has been sent to the resident with information from the Environment Team and Transgrid' legislative requirements in relation to the route through the Brookong State Forest. | ACT-60841 |  |  | Closed | 25/3/2024
2024 | 2024-04-09 | 1 |  |  | Phone call |  | Landowner H181 issued complaint regarding agreements made with the proponent still not honored, and recent off-easement access to his property. | Avoidable | EA Land Access Officer called Landowner to arrange access for access track work. The landowner indicated that he is locking his property and will not allow access to the commitments and compensation claim are honored. He also claims that vehicles have accessed his property without approval and off-easement. He intends to seek legal advice if an update is not provided regarding compensation claim. | • EA Land Access Officer has contacted the Proponent's Property Team and requested a meeting with Landowner to advise the status of the crop compensation and other commitments that the Landowner claims have been made by the Proponent. Awaiting Landowner to advise Proponent's Property Team of a convenient meeting time. • TG Land Officer contacted landowner on 10/4. New issues raised. Meeting to be booked with landowner to discuss resolution in-person. L/H meeting took place at EA office with TG and EA Land Access representatives on 23/4. | ACT-62988 |  |  | Closed | 2024-04-19
2024 | 2024-04-11 | 1 |  |  | Phone call |  | A representative of the Pappin Family Aboriginal Corporation issued a complaint in relation to RAPs from Barkindji Country carrying out heritage works in Balranald. | Unavoidable | EA Industry Participation Manager received a phone call from Pappin Family Aboriginal Corporation. A complaint was issued on the basis heritage works were being carried out on the PEC project by Barkindji Traditional owners, and that the Corporation was not given the opportunity to be engaged. | Everick confirmed with EA Participation Manager that no heritage works are currently being undertaken on PEC in the Balranald area. The Barkindji RAPs that the complainant is referring to appear to be engaged by a mineral resource company on an unrelated project. EA will advise the Pappin Family Aboriginal Corporation accordingly | ACT-63322 |  |  | Closed | 2024-04-11
2024 | 2024-04-22 |  |  |  | Phone call |  | Landowner on PEC called our Land Access Manager in the evening of 21 April and raised issues relating to project vehicle and road condition. | Avoidable | Issues raised in the call relate to the observation of speeding vehicles, the need for traffic management, the concern for potential for animal strikes, the condition of the local roads, and concerns over whether repairs will be completed. | EA Land Access Manager has advised Landowner he will investigate traffic management protocols in place with subcontractors, liaise with the Council Interface Team to understand dilapidation report cycle, and communicate the need for safe driving of all staff to the construction team via pre-start messages. |  |  | ACT-65398 | Closed | 2024-04-23
2024 | 2024-04-26 |  |  |  | Phone call |  | Landowner H124 on PEC called our Land Access Manager on 26 April alleging a survey peg had damaged a tire on his tractor. | Unavoidable | The landowner was undertaking a spraying program along the easement where his tractor struck a timber survey peg. The landowner is now seeking reimbursement of costs associated with the tire replacement, time to undertake repairs and loss of production time. | EA is investigating the issue to understand responsibilities with landholders undertaking cropping activities within the defined easement. Communication with the construction Team will also be undertaken to ensure once survey pegs are no longer required they are to be promptly removed. Survey pegs have been removed from the property and the tire is being repaired |  |  | ACT-65479 | Closed | 2024-04-10
2024 | 2024-04-26 |  |  |  | Phone call |  | Landowner who is not located on PEC called the 1800 number claiming he was unable "to get a word in" on Channel 14 because so many of Elecnor's subcontractors were using the channel. | Unavoidable | The landowner was undertaking sowing operations on his farm and said he was unable to communicate on Channel 14 because there were so many Elecnor Australia subcontractors using the same channel. | EA has investigated the issue and redirected all subcontractors to use Channel 17 instead. |  |  |  | Closed | 2024-04-29
2024 | 2024-05-01 |  |  |  | Meeting |  | Landholder H134 issued a complaint regarding vehicle traffic and condition of a local road. | Avoidable | A number of issues were raised in an on-site meeting between Landholder H134 (on L5), the Land Access Manager, and the OHTL Construction Manager. These included level of vehicular moments and the deteriorating condition of Webbs & Andriskies Lanes (between Lockart and Urana). The concern of road safety signage and traffic management was also raised. | All issues were noted by the Construction Manager and assurance was given to the L/H that mitigations would be put in place. A water tank arrived on site while the meeting was taking place.to address dust suppression in the Lanes The Construction Manager also indicated that water vehicles would make more regular visits to roads used by PEC. Consideration will also be given to using an alternative route going forward, and Supervisors will be reminded to ensure the use of traffic management signage by sub-contractors. Construction vehicles will now only access Webbs Rd from Boree Creek Rd |  |  | ACT-65965 | Closed | 2024-05-01
2024 | May |  | Thursday, 2nd | 11.08 am | Phone call |  | Landholder issued a complaint about the number of visits to the property for access track and tower pad construction, | Unavoidable | Land Access Officer was advised by H134 that there is to be no further tower foundation construction activities until all tower locations across the holding have undergone the assessment and approval process. The site has 14 towers and the L/H wants a consolidated tower construction program to limit impact on cropping activities. Permission has been granted to continue with access track construction only. | The Construction Team will attempt to bring forward inputs to assist with approvals across all locations. However, each site has to undergo the necessary approval process, which results in an extensive program across 14 towers. |  |  | ACT-66021 | Closed | 2024-05-02
2024 | May |  | Wed 10th | Tuesday - approx. 5pm | Phone call | L5 - Lockhart | Land Access Officer received a complaint from L/H 176 regarding a vehicle driving off easement. | Avoidable | .• The Land Access Officer received a call at approximately 5 p.m. yesterday to complain that a vehicle towing a port-a-loo had driven off the PEC easement area and used an internal track to exit the property onto the public road. Current PEC activities on the property are heritage-related. • L/H is concerned as the internal track is used to access the area on the property where the machinery, storage sheds and a property workshop are located – close to the homestead. | The Land Access Officer advised the LH he would follow up on this complaint with the Construction and Environment Teams, and re-iterate that vehicular access to the property is via the easement only. |  |  | ACT-66769 | Closed | 2024-05-10
2024 | May |  | Fri 17th | PM | Meeting | L5 | Land Access Manager and Officer met with LH205 at his office to discuss stock wondering from his property into neighbouring property via an opened gate. | Avoidable | .• L/H requested the meeting because some of the neighbour's sheep have tested positive to Brucellosis, and the L/H is concerned his rams may have contracted this disease. .• The L/H has contacted a Vet regarding the actions which could be implemented to protect the remainder of his sheep herd from contracting this disease (should any of the rams also test positive). L/H advised implementing these measure will incur operating and financial losses. | • Elecnor has agreed to investigate this matter internally to determine if this is a PEC matter, and meet with L/H again in week commencing 20th May. • L/H advised Land Access team that he is discussing testing requirements of his Rams with the Vet. • L/H contacted by Land Access Team on 22 May advising that they are still awaiting external IVMS records and will schedule meeting when records are received. |  | Commitment to meet with L/H and advise on IVMS record investigation to be tracked in Salesforce | ACT - 65470 | Closed | 2024-05-22
2024 | May |  | Fri 17th | 7am | Meeting | L5 - Lockhart | Land Access Officer met with LH183 at his property to issue a complaint regarding a vehicle driving off-easement to access heritage site. | Avoidable | • Land Access Officer & L/H inspected the PEC easement area to understand the locations where Heritage crews were utilising off-easement areas to access the PAD sites without L/H approval. This is the second time Heritage crew have used unauthorised off-easement access. • Also inspected area where the Heritage crew have erected flagging tape following the excavation activities. Observation made that lack of PEC access gates along the easement on property appear to have contributed to vehicles using off-easement access. | • Land Access Team to advise Construction Team to install PEC access gates in property boundary fences and fences exiting the easement area. • Land Access Team to liaise with Environment Team for solution that allows L/H access to his farming paddocks - currently restricted by the Heritage site exclusion flagging tape. • 23 May - Construction team agreed to install additional gates on property. Land Access Team to advise such with L/H. |  | Commitment to be made in Salesforce to complete additional gate installation and options for L/H for improved access to farming paddocks. | ACT - 68132 | Closed | 2024-05-23
2024 | May |  | Fri 24th | 8.50am | Email | Wagga | L/H 210 issued a complaint regarding concrete spill associated with access track construction. | Avoidable | Land Access Manager received an email at 8.50 AM on 24 May requesting that the spill be cleaned up and what is EA's action in relation to following the Environmental Plan. | • Land Access Manager acknowledged email at 10.04am that the request will be followed up with the Construction Team to action. • Construction Team removed the Pod during the week of 27 May and advised L/H but adjacent concrete residue remains. • Land Access Team to arrange Construction to return to site and collect remaining spill. |  | Concrete spill collection to be lodged as a commitment and tracked within Salesforce, and follow-up with Environmental Plan clarification. | ACT-68125 | Closed | 2024-06-06
2024 | May |  | Wed 29th | 1pm | Phone call | L5 - Lockhart | L/H181 issued a complaint regarding tree removal from his property. | Avoidable | The Land and Property Access Officer received an instruction in the morning from the L/H not to remove a tree from the property. This instruction was then communicated to the Construction Supervisors responsible for managing the Arborist program, and it was noted. However, the L/H contacted the Land Access Officer by midafternoon advising that the Arborist had removed the tree, and that he was very unhappy with the situation. | • The Land Access Team to investigate the issue with the Construction Team and respond to the L/H by the end of the week with an explanation of how the incident occurred, and to discuss next steps. • The Land Access team confirmed with the Construction Team that the tree was heavily trimmed before works by the contractor were ceased, and tree remains in situ. • 7/6 - Land Access contacted L/H to advise that tree position is under review by Environment Team against IA and EIS conditions and further advice will be provided following the outcome of the review - aiming to provide update to the L/H in the face to face meeting scheduled for 13 June. |  | Land Access team to confirm with Environment Team whether tree can remain and update L/H . Commitment to advise L/H to be tracked via Salesforce. | ACT-68412 | Closed | 2024-06-07
2024 | May |  | Fri 31 May | 9am | Meeting | L5 | L/H 185 issued a complaint regarding a number of issues including damaged gates, removal of mulch from trees that were incorrectly cleared, and the sourcing of replacement timber. | Avoidable | The Land Access Team met with the L/H to discuss the off-easement access approval currently in the Property Advice Statement. The L/H then raised dissatisfaction with a range of issues and requested: - Repairs to two damaged gates. - Replacement of timber from trees. incorrectly removed, - removal of the residual mulch from the property. | The Land Access Team to action requests made by L/H with the Construction Team. L/H to be advised of the timeline of repairs. 6/6- Land Access Team advised the L/H that gates have now been repaired. New timber has been actioned and mulch booked for removal by skip loader once ground conditions have dried following rain events. |  | Final removal of mulch and timber delivery to be tracked through Salesforce. | ACT-69232 | Closed | 2024-06-06
2024 | June |  | Sat 8th | 2.10pm | Phone call | L5 - Wagga | L/H 210 issued a complaint about gate on Redbank Road left unlocked. | Avoidable | Lessee of H210 called the Land Access Officer complaining that the padlock on the gate was left unlocked, and this has happened previously. He is concerned that gates left unlocked expose his cattle to potential theft. | The Land Access Officer visited the property on the same afternoon, threaded the chain through the lock and installed a second lock on the gate. The Leasee was advised accordingly. |  | The Construction Team will be notified and the driver last entering the gate will be identified and spoken with. Actions will be tracked through Salesforce. | ACT-70402 | Closed | 2024-06-08
2024 | June |  | Tuesday 11th | 05.00pm | Email | L5 - Wagga | Lockhart Shire Council has received a complaint about speeding vehicles along the Rock Lockhart Road at Tootool which is a village on the outskirts of The Rock. | Avoidable | A complaint has been made about speeding vehicles along the Rock Lockhart Road at Tootool. The vehicles are all marked but it is unclear what company that belong to. | Lockhart Shire Council will be contacted to find out more information about the vehicles that have been seen speeding and the name of the organisation on the vehicle. |  | The Construction Team will be notified once more information is received. | ACT-70524 | Closed | 2024-06-19
2024 | June |  | Friday 14th | 8.10am | Text | L5 | Mud on public road from PEC vehicles. | Avoidable | L/H 210 contacted Land Access Manager advising PEC vehicles from S3 had dropped mud on Ashfords Road, and requested clean up. | Land Access Manager advised Construction Team. A crew was sent to Ashfords Road and the site was cleaned at 1pm. L/H advised accordingly. The incident will be investigated and a Report issued to the L/H. |  | The report will be identified as a commitment in Salesforce and sent to L/H when complete. | ACT-70858 | Closed | 2024-06-14
2024 | June |  | Mon 24th | 12.09pm | Phone call | L5 | Speed of PEC vehicles on Yuluma Rd (near Lockhart) | Avoidable | L/H 141 contacted Land Access Officer complaining that the operators of the concrete trucks, H/V’s and L/V’s are travelling at a speed along Yuluma Rd that is not taking into consideration local traffic or the narrow width of the roads. L/H requested that Elecnor address this issue and advise drivers to slow down. L/H would also like an update on actions taken. | Land Access Team to raise issue with OHTL Construction Team and request information on actions taken to correct, and enable feedback to the L/H. 28/6 - HS advised and pre-start Briefing Note issued alerting construction teams to issue of speeding vehicles. 5/7 - Land Access Officer delivered Briefing Note to L/H 141 as proof action was taken. |  |  | ACT-71761 | Closed | Fri 28th
2024 | June |  | Fri 28th | 2.40pm | Email | L5 | Vehicle Speed Complaint regarding Yuluma Rd/Lockhart-Boree Creek Rd Boree Creek | Avoidable | A community member lodged a complaint via theTransgrid website complaining about travelling speed of project vehicles on Yulumna Road and Boree Creek Road. The community member also informed the project that they will be moving sheep between farms all weekend and want to ensure drivers were aware and drive accordingly. | The Trangsgrid Engagement Team member advised the community member that Elecnor have raised the issue with the Construction and Land Access Teams. Information regarding the sheep will be shared at the pre-start and communication issued to vehicle operators about the requirement to travel safely and to be mindful of local conditions. 28/6 - HS advised and pre-start briefing note issued alerting construction teams to issue of speeding vehicles. 5/7 Land Access Officer delivered Briefing Note to L/H 141 as proof action was taken, |  |  | ACT-72899 | Closed | Fri 28th
2024 | June |  | Fri 28th | 9.02am | Phone call | L5 | Complaint regarding unauthorised access to perform construction-related activities. | Avoidable | L/H181 issued a complaint to the Elecnor Land Access Officer about a range of issues covering recent access to the property, notification and outstanding compensation. | Several correspondences were made with L/H's representative advising the access rights granted under the authorised Option Agreement. Action items from a previous meeting were also discussed and are still be implemented. 9/7 - Elecnor Commercial sent email to L/H representative with an update on mitigation measures raised in 13 June meeting. Construction will now be managed as per PMP conditions. |  | Confirm any outstanding actions and advise L/H and representative of status. | ACT-73270 | Closed | 2024-07-09
2024 | July |  | Fri 5th | AM | Meeting | L5 | Complaint from landholder about the waste of tax payers' money he is observing on the project. | Unavoidable | Landholder for H128 & H134 advised the Land Access Officer in a meeting that he is concerned at the manner in which activities associated with PEC are been managed throughout the local area. He claims to see waste with idle machinery, idle workers and hold-ups caused by heritage works. He advised the Land Access Officer that he intends to report this to the media next week. | Land Access Officer to investigate with Engagement and Construction Teams, and respond to L/H accordingly. 6/7 - Contacted the L/H and advised will be calling on Monday to arrange a meeting. 10/7- Land Access Manager spoke with L/H and listened to concerns. They agreed to a meeting w/c 15 July where a Construction and Environmental Manager will also attend. |  | Response to L/H | ACT-23275 | Closed | 2024-07-16
2024 | July |  | Mon 8th | AM | Phone call | L2 | Delayed reimbursement of gate installation costs and concerns that surveyors had pegged easement via access from 2090. | Avoidable | Land Access Officer phoned H091 to advise that the invoice included an error and payment will be delayed to next payment run. L/H complained about the delay in follow-through from the Construction Team that agreed to the gate installation program, and will soon prevent access if not settled. The L/H also expressed concern that surveyors had accessed his property and pegged the access track from AP2090 to the easement without prior approval. | Invoice has been re-submitted and expected to be paid by 12th July. Land Access team to advise the construction team of L/H's pre-approval required to access 2090. 11/7 - Payment processed to the L/H. |  | Awaiting feedback from Construction team. | ACT-71761 | Closed | 2024-07-11
2024 | July |  | Mon 8th | 8.15am | Phone call | L2 | Survey flagging and taping | Unavoidable | Land Access Office called H085 to arrange additional access from North Boundary Rd as PEC easement was very wet. L/H raised concern about survey pegs and flagging tape as he believes it could be a hazard to his staff when operating machinery during mustering. Requested a review of the pegging and removal of the flag tape. | Land Access Officer to investigate with Heritage Team and advise L/H of outcome. New high-vis tape to be installed that will reflect and be more visible. Land Access Manager advised new flagging option to landholder and meeting is being planned on-site to discuss. |  | Advise L/H on 15 July | ACT-73278 | Closed | 2024-07-15
2024 | July |  | Tue 9th | Am | In person | L5 | Dust from passing vehicles on Henderson Rd Tootool. | Avoidable | A community member approached a Transgrid staff member at The Rock around lunchtime advising of a dust issue on Henderson Road, Tootool during dry weather. He requested the deployment of a water truck in future to for dust suppression.. | The Transgrid Land Access Officer notified Elecnor Construction Team and requested the use of a Water Truck. Currently, there are no dust issues due to rainfall but the Team will ensure a water truck undertakes visits to Henderson Road to mitigate dust. |  | Elecnor Engagement Team to confirm mitigations with Construction Team. |  | Closed | 2024-07-10
2024 | July |  | Thur 11th | AM | In person | L5 | Community member issued a complaint relating to range of issues including project vehicles, noise emanating from the camp, traffic control and Access communication during in the planning phase of the project | Unavoidable | A community member who resides at Sly's Lane, near the Lockart camp, visited the Discovery Hub and complained to the Transgrid staff, raising a range of issues with PEC operations. The Transgrid staff member acknowledged the complaint and advised that Elecnor would contact him and respond accordingly | EA Engagement Manager contacted the community member on 12 /7 to investigate. The Engagement Manager than contacted the Environment and Construction Team and was advised that a noise assessment will be completed to determine next steps. 19/7 -Permits have been reviewed and a noise easement conducted on site. |  | Advise community member of the assessment outcome and email supporting correspondence. | ACT-73755 | Closed | 2024-07-19
2024 | July |  | Friday 12th | AM | In person | L5 | Condition of local roads | Avoidable | TG Land Access Manager advised Elecnor that H124 issued a complaint during a discussion about deteriorating Shire gravel roads due to PEC vehicles. | Elecnor awaiting email from L/H to determine specific roads and then will investigate with the Council Interface Team. 18/7 - Elecnor Land Access Officer called L/H and advised of the local road delipdation reporting that is taking place in August and the subsquent action that are taken to address any repairs. L/H was comfortable with this mitigation. |  |  | ACT-65398 | Closed | 2024-07-18
2024 | July |  | Thursday 18th | 1.55pm | Phone call | L5 | Use of Communication Channel | Avoidable | Lockhart Mayor Greg Verdon contacted Elecnor to make a complaint on behalf of the Farmers' Federation. The Federation advised the Mayor that farmers at Lockhart are frustrated by the number of construction people using Channel 14. | Elecnor is moving all subcontractors from Channel 14 to Channel 13 on a one week trial. If it is successful, Channel 13 will be used going forward. |  | Elecnor to use Channel 13 as a trial for the next week. If it is successful, Elecnor will stay on this channel. Channel 14 will only be used in an emergency such as a fire. The Lockhart Mayor has been advised. | ACT - 74582 | Closed | 2024-07-18
2024 | July |  | Thursday 18th | 2.00pm | Phone call | L5 | Gate left open | Avoidable | H196 called EA Land Access Officer advising that the boundary gate between his property and H195 was left open, L/H advised that all gates are to be left as found and that this is a warning for not adhering to the PMP. | Land Access Officer advised the L/H that he would install gate open/close signs tomorrow (19/7) at the property. L/H agreed to the mitigation. 19/7 Gate signage installed with the L/H. Land Access construction of the need to remain vigilant with gate procedures. |  | Ensure pre-start briefing captures messages on new gate signage. | ACT - 74586 | Closed | 2024-07-19
2024 | July |  | Friday 19th | AM | In person | L5 | Vehicle cleanliness upon entry to property | Avoidable | While the Land Access Officer was installing gate signage with the L/H 196 as a mitigation to a previous complaint, a number of civil works sub-contractors arrived with vehicles that did not meet the 'come clean go clean' requirements. The L/H advised that if biosecurity measures are not adhered to as per the PMP, the gates will be locked. | 19/7 - The Land Access Officer and Engagement Manager immediately raised the issue with the Construction Team and will determine mitigations to reinforce 'come clean, go clean' requirements across the subcontractor crews. The L/H will be advised accordingly. 25/7 - L/H advised that construction staff have been briefed at pre-starts of biosecurity requirements when entering and exiting property. Landholder indicated he was satisfied with this mitigation. |  |  | ACT- 74690 | Closed | 2024-07-25
2024 | July |  | Mon 29th | 3pm | In-bound text | L2 | Gate left open | Avoidable | EA Land Access Officer received a text from L/H085 advising that a gate along North Boundary Road was left open. L/H expressed concern that an open gate on this boundary fence could allow cattle to exit into a public area | 29/7 - The Land Access Officer acknowledged the text and notified the construction team. The L/H will be advised of subsequent actions and planned mitigations. 2/8 - Land Access Office called and advised that the issue has been raised with the construction Team and will be highlighted at pre-starts and reminders given to all sub-contractors. The L/H was comfortable with the actions taken. |  |  | ACT-75149 | Closed | 2024-08-02
2024 | July |  | Tues 30th | 9pm (29th July) | Email | L2 | First Nations Community member sent an email expressing disappointment on not being engaged for an event. | Unavoidable | At 9pm on 29th July we received an email from a member of the Southern West Yiradyuri Corporation who expressed a complaint against our decision to engage another First Nations person to provide cultural services at an internal event. | 30/7 We acknowledged the complaint and advised we will respond formally with an email providing further explanation of our event planning. 31/7 Engagement Manager emailed the complainant expaling the event management process and highighted the intent was not to cause disrespect to the coporation by procuring the servcies by another supplier. |  |  | ACT-75195 | Closed | 2024-07-31
2024 | August |  | Fri 2nd | 8.20pm (1 Aug) | Phone call | L5 | Damaged water pipe on landholder's property during earthworks | Avoidable | At approx 8.20pm, the Land Access Officer received a phone call from the Landowner H126's son advising a damaged water pipe during the day resulted in no water supply to the residence overnight. | 1/8 - The Land Access Officer apologised and notified the Construction Team of the complaint and requested repairs to be immediately made the next day. 2/8 - The repair was actioned in the morning and new fittings applied to the pipe. Water supply was restored. The Land Access Officer advised the Landholder accordingly. The Land Access Team reiterated to the Construction Team the need to refer to Property Management Plans prior to earthing works. The Team are also planning on conducting an onsite meeting with the Landholder and her son to apologise again in-person for the disruption and inconvenience. |  |  | ACT-76183 | Closed | 2024-08-02
2024 | August |  | Fri 9th | 8.00am | Phone call | L5 | Work crews accessing L/H property prior to agreed access time and not following agreed bio-security procedures. | Avoidable | Land Access Officer received a call from H189 advising the workers had entered the access track prior to the agreed time without permission. As a consequence, the L/H has indicated the access gate will be locked for next seven days because agreed procedures were not followed. | 9/8 - The Land Access Officer travelled to site to investigate, and advise Construction Management of the issue. The L/H was advised the issues has been escalated. Construction to advise on mitigations following investigation. 21/8 - Land Access met with L/H and advised of investigation status. Mitigations such pre-start briefing with Subcontractors been made aware of the obligation on property access requirements with H189. |  |  | ACT-76887 | Closed | 2024-08-21
2024 | August |  | Mon 12th | 7.10pm | Phone call | L2 | Gate left open on H084 and cattle found outside the property | Avoidable | Land Access Officer received a call from H084 on Monday at 7.10pm advising that a gate had been left open and cattle had left property. The L/H retrieved the cattle and returned them to the property. The L/H also raised the issue that gates are being installed in areas along the fence line that could be better placed and utilise the current gate positions that access the existing 220kv line. | 12/8 Land Access Officer has apologised to L/H and raised the issue with L2 Construction to reiterate gate protocols at pre-starts. 13/8 - Land Access officer visited property owner on site and discussed issue and agreed to create awareness among Construction Team and made a committment to install a high-vis sign on the gate to assist with gate closure. |  |  | ACT-78011 | Closed | 2024-08-13
2024 | September |  | Mon 2nd | AM | In an outbound phone call | L5 | Condition of access track construction and surveyor on property without prior notification. | Avoidable | Land Access Officer called L/H 196 to discuss access track. During the call, the L/H advised that the track still poses a safety risk due to its condition. He also complained that a surveyor was on the property with notification as per agreed access requirements. He advised that any additional breaches in access requirements will result in the gates being locked. | 2/9 - Land Access Officer notified the L5 Construction Team of the issue and will investigate a solution and potential mitigations. 5/9 - Advise L/H that rectifications works were being scheduled. 14/9 - Works carried out on the access track to smooth edges and remove any potential risks to farming equipment. |  |  | ACT-79448 | Closed | 2024-09-14
2024 | September |  | Mon 2nd | 8am | Phone call | L5 | Spoil from tank excavation still remaining on the property. | Avoidable | Land Access Officer received a call from L/H082 again requesting the removal of spoil from the property (1st request made in July). | 2/9 - Land Access Officer contacted the Construction Team and was advised that a subcontractor will be booked to clean up the spoil tomorrow. 11/9 - Land Access Officer received an email from the Construction Team advising the spoil was removed and relocated as per L/H's request. While on the property, the team also rectified a leak on the tank. |  |  | ACT-79441 | Closed | 2024-09-11
2024 | September |  | Tue 10th | 8am | Phone call | L5 | The use of inappropriate language in the presence of a landowner. | Avoidable | A complaint was raised with the Land Access Manager regarding the use of inappropriate language in the presence of L/H189 when a construction staff member was asked to clean the vehicle before entering the property. | The Land Access Manager acknowledged the complaint and will investigate the issue with the Construction Team Leader. The Construction Team advised the Engagement Manager that the complaint is not accurate. The Land Access Manager issued an apology to the L/H on behalf of the project and highlighted that courteous delaings with all stakeholders is an expected behaviour on the project. |  |  | ACT-80833 | Closed | 2024-09-17
2024 | September |  | Sun 22nd | 9.30am | Text | L5 | Survey pegs in cropping area | Unavoidable | The Land Access Officer recieved a text in the morning (Sunday) from L/H124 expressing comcerns about survey pegs remaining in cropping areas. The L/H believes the 100mm protruding above the surface represents a risk to cropping machinery and safety. | The Land Access Officer acknowledged the complaint via text, and notified the Construction Team. A solution will be investigated on Monday and next steps advised to the L/H. 1/10 - Construction team have actioned the temporary removal of pegs to allow harvesting activities. |  |  | ACT- 81656 | Closed | 2024-10-01
2024 | September |  | Mon 23rd | 9.00am | Phone call | L5 | Heritage pickets and crops | Unavoidable | L/H 176 called the community1800 line complaining about the emerging H&S risk with the heritage bunting and star pickets in the crop | The Engagement Team member acknowledged the complaint and advised the L/H that the issue will be raised with the Land Access and Construction Teams. The next steps will be advised once the mitigation has been addressed. 4/10 - Construction team have actioned the temporary removal of pegs to allow harvesting activities. |  |  | ACT-82903 | Closed | 2024-10-04
2024 | September |  | Mon 23rd | 10.00am | Phone call | L5 | Quality of gate installation | Avoidable | The Land Access Officer received a call from H082 who was complaining that the fence connecting the gate between structures 147 and 148 was not tensioned properly. As a consequence, the posts were bent over and the lower wire was loose. The L/H also indicated that he came across a project worker climbing over the mesh fence near the tank farm. | The Land Access Officer will investigate with the Construction Team and advise the L/H on next steps with the repair. 1/10 - Repairs undertaken by Construction Team and a meeting planned for 4 Oct. |  |  | ACT- 81681 | Closed | 2024-10-01
2024 | September |  | Wed 25th | 5.30pm | Phone call | L5 | Foundation spoil on tower pad | Avoidable | The Land Access Officer received an after-hours call from L/H H176 advising of his concern that foundation spoil is being placed in the centre of the tower pads on his property. As the L/H will be cropping in these areas in the future he previously requested that the spoil be placed elsewhere. This request was reflected in the Property Advice Statement (PAS) and Property Management Plan (PMP). | The Land Access Office advised he will raise the issue with the Construction Team and respond accordingly with next steps. 2/10 - Construction Team agreed to address pad issue by re-grading site and reduce the profile and remove suplus soli. Works scheduled for w/c 7 October. |  |  | ACT-82052 | Closed | 2024-10-02
2024 | September |  | Friday 27th | 9.00am | Email | L2 | Noise, light and number of people to live at the Cobb Highway camp | Unavoidable | A sensitive receiver to the Cobb Highway camp emailed to advise of the increase in noise from the camp. They also said they had been told inaccurate information in relation to the number of personnel at the camp. They also raised the issue of light from the camp being seen from their home. | The Engagement Team has raised the issue with Construction and Environment Teams and they will respond with next steps. 11/10 - The Environment Team is arranging noise monitoring at the community member's property to validate noise levels. The Community Stakeholder Lead is now liaising with the resident to agree on a preferred time. |  |  | ACT-82327 | Closed | 2024-10-11
2024 | October |  | Friday 10th | 4.45pm | Email | L5 | Collision between PEC contractor concrete truck and community member vehicle | Unavoidable | Transgrid Community Team emailed the Elecnor Engagement Team with a complaint lodged from a community member alleging a concrete truck collided with his box camper trailer on Brookong Creek Road near Urana on Thursday 9th October, and then drove off. | The Engagement Manager acknowledged the complaint with the community member and also inquired with the Construction Team and Concrete Contractor. The incident has been recorded and will be investigated next week by the Contractor and Safety Teams. 10/10 - The concrete contractor is now liaising with the community member. The investigation is underway and they the parties will agree on the accident resolution process once the investigation is complete. Elecnor will remain as the escalation point for the community member who agreed to this approach. |  |  | ACT- 82094 | Closed | 2024-10-10
2024 | October |  | Saturday 5th | 10.50am | Phone call | L5 | Use of off-easement access track | Avoidable | Land Access Officer received a call from L/H177 advising that a survey vehicle had been seen using an access track off-easement. The driver claimed he was lost. L/H advised that if this continues he will only allow access when requested and will lock the gate in between these instances. | The Land Access Officer acknowledged the complaint. The issue will be raised with the Construction Team, who will then re-iterate the surveyors can only access the property easement by the approved tracks. 16/10 - Land Access Officer advised the L/H that the Contruction Leader has been instructing staff at morning pre-starts not to use tracks off-easement and to access towers along the easement only. The L/H advised the Land Access Office he was with this action. |  |  | ACT-82905 | Closed | 2024-10-16
2024 | October |  | Monday 14th | 5.30pm | Email | L2 | Breach of Wiradjuri cultural protocols | Unavoidable | EA First Nations Participation Manager received an email complaint from a Local Aboriginal Land Council at 5.30pm. The concerns raised related to alleged breaches of engagement protocols such as the use of Wiradjuri language in the naming of Camp 3 and non-engagment of labour services. | The First Nations Participation Manager acknowledged the email later that evening and actioned the complaint escalation the following business today with Elecnor's client. A meeting invitation has been extended to the CEO of the LALC for next week where the issues raised will be discussed. 28/10 - Meetung conducted with the CEO and discussed the issues. Transgrid and Elecnor will look for opportunities engage golng forward which may include for exmapleTG's Communigty Partnership program, Cultural Heritage Training on the project. Momnth meetings have also been set going forward. |  |  | ACT-83620 | Closed | 2024-10-28
2024 | October |  | Thursday 17th | 11.49am | Email | L5 | Drunken behaviour by subcontractors based at Lockhart camp | Avoidable | A small group of about 10 people, some wearing PPE attended the Spirit of the Land Festival on Saturday night where they observed to be intoxicated and acting inappropriately in front of community members. | Elecnor will now investigate this matter. 31/10 - |  |  | ACT-83881 | Closed | 31/10
2024 | October |  | Thursday 17th | 8.37am | Text | L5 | Gate left unlocked and vehicle hygiene sheet not signed | Avoidable | Land Access Officer received a text from H210 advising that a gate off Renmark Road was left unlocked by PEC work crews. Vehicle hygiene sheets are also not being signed. The property lessee is concerned as he has cattle on the property and indicated that crews must adhere to gate protocols or the issue will be escalated. | The Land Access Officer advised he will raise this with Construction crews and have the message communicated at pre-starts. The lessee advised he is happy with this action. |  |  | ACT-83941 | Closed | 2024-10-17
2024 | October |  | Thursday 17th | 11.15am | Email | L5 | Driving incident involving PEC vehicle | Avoidable | Transgrid received a complaint on their Community Line regarding a construction vehicle narrowly missing a bus when turning out of an intersection on Boree Creek Road. | Following an investigation of the vehicle rego number by the Elecnor Construction Team, it was confirmed that the vehicle was part of a PEC subcontractor fleet. The construction worker driving the vehicle turned out of the intersection without looking left and due to the narrow width of the road, a bus had to brake suddenly and swerve off the side of the road. The Contruction team confimed they will reiterate at pre-starts the need for safe driving practices. The Project Interface team confirmed they will inquire with the local council about the possibility of additional signage at the intersection. These steps were communicated to the complainant who was comfortable with the investigation and steps to be taken. |  |  | ACT-83990 | Closed | 2024-10-17
2024 | October |  | Thursday 17th | 5.00pm | In person | L5 | Driving incident involving PEC vehicle | Avoidable | A community member attended a Pop Up at Urana to advise she had contacted Transgrid regarding a construction vehicle narrowly missing a bus when turning out of an intersection on Boree Creek Road. | Following an investigation of the vehicle rego number by the Elecnor Construction Team, it was confirmed that the vehicle was part of a PEC subcontractor fleet. The construction worker driving the vehicle turned out of the intersection without looking left and due to the narrow width of the road, a bus had to brake suddenly and swerve off the side of the road. The Contruction team confimed they will reiterate at pre-starts the need for safe driving practices. The Project Interface team confirmed they will inquire with the local council about the possibility of additional signage at the intersection. These steps were communicated to the complainant who was comfortable with the investigation and steps to be taken. |  |  | ACT-83937 | Closed | 2024-10-17
2024 | October |  | Thursday 24th | 11.05am | Email | L2 | Road safety | Avoidable | A Balranald community member sent an email to PEC's Camp 5 onsite manager complaining about driver behaviour .The issue raised was that some drivers who turn right out of the camp and travel along Church Street are not giving way as they cross over River or Bank Streets - rasing the safety risk to pedestrians or other road users. | The Camp Manager acknowledged the complaint and advised the resident that they will forward the complaint to the H&S Manager. The H&S Manager raised the issue with the Community Engagement, Construction and wider H&S teams. The safe driving message will be communicated at Camp 5 pre-starts and crews will be instructed to turn left out of the camp to avoid the residential areas. The resident was comfortable with the actions taken and how the complaint was escalated |  |  | ACT-84549 | Closed | 24/10
2024 | October |  | Thursday 24th | 3.05pm | Email | L5 | PEC fencing contractor | Avoidable | LH188 lodged a complaint via the TG Community line regarding the TG property area and contractors conducting works on his property. | The TG Community Team acknowledged the complaint and forwarded the correspondence to EA Engagement Team. The Land Access Officer to investigate the issues raised with the L/H. 5/11 - Land Acess Officer is arranging a meeting with L/H to go through each issue. |  |  | ACT-84605 ACT-84583 | Closed | 2024-11-05
2024 | October |  | Friday 25th | 9.15am | SMS | L5 | Gate left open | Avoidable | Land Access Officer received a text from H210 advising that a gates at Structure 1 have been left open and vehicle hygiene sheets have not been signed. The property lessee is concerned as he has cattle on the property and some may wonder onto the Boiling Down Road if the gate is left un attended for any length of time. The Lessee said he will lock the gate if not addressed. | The Land Access Officer acknowledged the complaint and contacted the Construction Team. The issue will be raised pre-starts again. Following the pre-start, the EA Civil Superintendent will call a meeting with Supervisors, Superintendents, Managers, and Leading Hands of all delivery partners to address this matter. |  |  | ACT-84603 | Closed | 2024-10-31
2024 | October |  | Sat 26th | 5.06pm | Phone call | L5 | Plastic left in paddocks | Avoidable | H122 called the Land Access Officer requesting that all plastic to be picked up out of his paddocks left from work crews. He is concerned his expensive cattle may be at risk if they began to eat the plastic. | The Land Access officer contacted the Construction Team and advised them of the issue. The Superintendent deployed a work crew to the property to clean the site and secure boxes. The issuewas flagged through pre-start to all A&E crews that boxes must be contained and sites left tidy each day. |  |  | ACT-84610 | Closed | 2024-11-06
2024 | October |  | Sat 26th | 2.40pm | Voice mail | L5 | Plastic left in paddocks | Avoidable | Land Access Officer received a voicemail from H181 complaining that plastic sheets were left in his paddocks. Landholder collected these and gave them to an Elecnor employee who was onsite. | Land Access officer contacted Construction Team advising of the issues. The matter will be investigated and teams will be informed. The construction crew attend the matter by collecting plastic. The issue was flagged through pre-start to all A&E crews that boxes must be contained and sites left tidy each day. |  |  | ACT-84609 | Closed | 2024-11-07
2024 | October |  | Sunday 27th | 11.30am | Phone call | L5 | Work being carried out without the landholders permission. | Avoidable | The landholder's representative (H176) phoned to advise that Elecnor contractors were working on the property on Sunday 27/10/2024 without seeking permission from the Landholder to work outside of the agreed working hours. They also advised that thi situation has occurred on a number of occasions over the last few weeks. They mentioned that they felt they were not being treated with respect by the Contractor | The Land Acess officer advised the landholder that the matter would be raised with senior management and the construction team. Mitgations will include that the Construction Team notify the Land Access Team a minimum of 48 hours prior to the planned works so that permission can be obtained from the landholders impacted by these works. The Construction team also agreed that works will be undertaken withing standard approved hours until further notice. |  |  | ACT-84671 | Closed | 2024-11-11
2024 | October |  | Tuesday 29th | 10.35am | Text | L2 | Harvesting machine damaged by peg when cutting crop in project area. | Unavoidable | L/H for H047, 48, 50 advised Land Access Officer that his grain harvester's comb and knife was damaged after striking a survey peg when cutting the crop within project area. L/H advised he would be seeking costs for repairs and delays. | Land Access Officer acknowledged the complaint and will follow up with the Construction, Environment and Commercial Teams to determine next steps. The Land Access Officer spoke with the L/H who advised that he was busy and would like to discuss the matter after havesting activities and whether he would seek replacemnent of the cutting knives. |  |  | ACT-85989 | Closed | 2024-11-04
2024 | October |  | 31/10 | 3.30pm | In person | L5 | Etiquette shown by PEC contractors at community gym in Hay | Avoidable | Complaint made by a Hay Council employee to Transgrid about the etiquette shown in the community gym by construction workers from Camp 4. Transgrid have forwarded the complaint to Elecnor and asked to follow up. | PEC Community Engagement Team will investigate the complaint with the Camps Team and follow-up with the complainant. 5/11- The Camps Construction team advised the subcontract group who were utlising the local gym have demobilized from site last week and will not be returning to site. |  |  | ACT-86737 | Closed | 2024-11-05
2024 | October |  | 31/10 | 10.25am | Text | L5 | Vehicle hygene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a text from LH 188 regarding a vehicle he had to turn away from his property due to vehicle hygiene. L/H expressed bio security conerrns. The vehicle returned for a second time but was rejected again. | Land Access Officer acknowledged the complaint and will raise an investigation with the Construction Team to identify the sub contractor and driver. 4/11 - Complaint entered into incident reporting system and escalated to Envrionment Team. Land Access Officer contacted L/H who was happy with the escalation process. |  |  | ACT-85102 | Closed | 2024-11-04
2024 | November |  | 2024-11-02 | 1.50pm | Call | L5 | Complaint from Land Holder that Construction crew were working out of approved hours on the property. | Avoidable | Land Access Officer returned a missed call from H176 and was advised that Elecnor were working outside of agreed construction hours on Saturday.The Site Supervisor removed the crew from Tower 90. | Land Access Officer acknowledged the complaint and advised the L/H that he would look into the issue with the Envrionmental and Constructions Teams and be back in contact with the update on the Enviromental Permits. 11/11 - Envrionment Permit covers OOWH activity on the property (excluding one tower). However, the Construction Team will maintain standard approved construction hours for PEC activities until further notice. |  |  | ACT-85286 | Closed | 2024-11-11
2024 | November |  | 2024-11-03 | 5.28pm | Text | L5 | Vehicle hygiene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a text from LH 188 regarding Land Survey Vehicles and concrete trucks he had to turn away from his property due to not meeting minimum vehicle hygiene standards. L/H expressed bio security concerns and would like vehicles inpected before leaving camp as he is spending time completing the task himself. | Land Access Officer acknowledged the complaint and will work with the Construction Team to identify a process that mitigates this issue. 4/11 - Complaint entered into incident reporting system and escalated to Envrionment Team. Land Access Officer contacted L/H who was happy with the escalation process. |  |  | ACT-85290 | Closed | 2024-11-04
2024 | November |  | 2024-11-04 | 11.25 am | Text | L5 | Vehicle hygiene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a text from LH 188 regarding Land Survey Vehicles and concrete trucks he had to turn away from his property due to not meeting minimum vehicle hygiene standards. | Land Access Officer acknowledged the complaint. The issue was also logged in Elecnor's incident management system. The Construction Team are investigation enhanced protocols to ensure vehicle hygiene standards. 4/11 - Complaint entered into incident reporting system and escalated to Environment Team. Land Access Officer contacted L/H who was happy with the escalation process. |  |  | ACT-85575 | Closed | 2024-11-04
2024 | November |  | 2024-11-06 | 2.30pm | Meeting | L5 | Unsafe condition of the access track left by Elecnor | Avoidable | The Land Access Officer met L/H 196 following a report that he had contacted Safe Work NSW about the condition of his access track. L/H has previously requested the edges of the track to be made-safe for quad bikes and LV to cross. Berns also need to be installed to slow water run off and to stop erosion. Instruction for the track to be made safe within 7 days. | Land Access Officer acknowledged the complaint and contacted the Construction Team. The Engagement Manager has advised Safety and issue is now being attended to. 19/11 Construction Team completed mediation works to the track. L/H satisfied with the result. |  |  | ACT-86836 | Closed | 2024-11-19
2024 | November |  | 2024-11-06 | 6.25pm | Text | L5 | Vehicle hygiene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a text from LH 188 regarding Land Survey Vehicles and concrete trucks he had to turn away from his property due to not meeting minimum vehicle hygiene standards. | Land Access Officer acknowledged the complaint. The complaint will be added to the other reported non-conformance incidents as part ot the investigation 18/11 - Land Access and Construction Team met with L/H to discuss recent vehicle issues. New mitigations proposed included extra equipment at washdown bay and the appointment of a dedicated supervisor to oversee vehicle inspections and bio security conformance. |  |  | ACT-85698 | Closed | 2024-11-18
2024 | November |  | 2024-11-11 | 8.09am | Phone call | L5 | Harvesting machinery struck wooden block (dunnage) which had been left in the cropping area. | Avoidable | L/H 173 contacted Land Access Officer advising that while harvesting the canola crop, the machinery picked up a wooden block. The block was removed from the header elevators and no major damage detected. The landholder found six more blocks lying in the crop, which caused a 2.5 hour delay to operations. | Construction supervisors to be notified of the incident. Site inspection & cleanup to be instigated. 20/11 - Land Access Officer completed a site inspection and found no other timber in the crop. Raised the issue at pre-start on 13/11/2024 |  |  | ACT-86074 | Closed | 2024-11-20
2024 | November |  | 2024-11-14 | 3.30pm | SMS | L5 | Vehicle hygiene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a text from LH 190 regarding project vehicles she had to turn away from her property (access neighbouring property) due to not meeting minimum vehicle hygiene standards. | Land Access Officer acknowledged the complaint and has advised the Construction Team. He also advised of upcoming improvement mitigations. 18/11 - Land Access and Construction Team met with L/H to discuss recent vehicle issues. New mitigations proposed included extra equipment at washdown bay and the appointment of a dedicated supervisor to oversee vehicle inspections and bio security conformance.L/H advised she was comfortable with the new mitigation approach. |  |  | ACT-86572 | Closed | 2024-11-18
2024 | November |  | 2024-11-14 | 12.30pm | Call | L5 | Vehicle hygiene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a call from LH 188 regarding project vehicles he had to turn away from his property due to not meeting minimum vehicle hygiene standards. L/H requested meeting to discuss issue and work through mitigations | 18/11 - Land Access and Construction Team met with L/H to discuss recent vehicle issues. New mitigations proposed included extra equipment at washdown bay and the appointment of a dedicated supervisor to oversee vehicle inspections and bio security conformance. L/H advised he was comfortable with the new mitigation approach. |  |  | ACT-86557 | Closed | 2024-11-18
2024 | November |  | 2024-11-15 | 8.10am | SMS | L5 | Vehicle hygiene and non-conformance with come clean, go clean requirements | Avoidable | Land Access Officer received a text from LH190 regarding sub contractor vehicles that she rejected from accessing her property due to not meeting hygiene standards. | Land Access Officer acknowledged the complaint and advised the Construction Team. Land Access Officer also met with subcontractor crew highlighting the requirement for minimum vehicle hygiene standards. The contractor's Construction Lead advised that the crew would return tomorrow with washed vehicles. 18/11 - Land Access and Construction Team met with L/H to discuss recent vehicle issues. New mitigations proposed included extra equipment at washdown bay and the appointment of a dedicated supervisor to oversee vehicle inspections and bio security conformance. L/H advised she was comfortable with the new mitigation approach. |  |  | ACT-86572 | Closed | 2024-11-18
2024 | November |  | 2024-11-18 | 9am | Phone call | L5 | Access track construction restricting natural water flow | Avoidable | Land Access Officer received a call from H195 complaining that the access track diverted the water from recent rains away from the nearby dam and into a recently-planted crop. The waterlogged area may impact seed germination. | The Land Access Officer acknowledged the complaint and then inspected the site with the L/H's representative. The Construction team were notified and they will instruct the sub-contractor to complete remedial works. 19/11/2024 Rectification works commenced and was completed in three days resolving the water flow restriction issue. Landholder advised he was comfortable with the solution. |  |  | ACT-86728 | Closed | 2024-11-28
2024 | November |  | 2024-11-20 | 7.30am | Phone call | L5 | Speeding driver identified by a truck driver who regularly travels between Lockhart and Albury. | Avoidable | A truck driver contacted the 1800 community information number to advise he had witnessed a speeding driver on the Lockhart Road to Urana, | PEC's Fleet Manager has confirmed this vehicle number is used by subcontractors. A meeting with this subcontractor has taken place to discuss issue and safe driving reiterated at daily pre-starts. |  |  | ACT-86885 | Closed | 2024-11-20
2024 | November |  | 2024-11-21 | 7.45am | Phone call | L5 | PEC employee using off-easment track | Avoidable | Land Access Officer received a phone call from H176 complaining about a PEC employee using an internal property track instead of the easement. L/H approached the employee who advised he is new to the project and thought he was following the supplied map. | The Land Access Officer apologised to the L/H and advised the new employee of the correct access track to the easement. Staff member's supervisor also advised of L/H's complaint and requirement to stay on easement. |  |  | ACT-87241 | Closed | 2024-11-28
2024 | November |  | 2024-11-28 | 2.30pm | Phone call | L1 | PEC vehicle not slowing down near livestock | Avoidable | Land Access Manager received a phone call from H013 advising that a PEC water truck travelling on Arumpo Road did not slow on when he saw livestock on the side of the road. Consequently, lambs split from the mob and damaged a fence. | The Complaint has been acknowledged and will be investigated. Issue to be raised with Camp 6 Construction Team and highlighted at pre-starts. |  |  | ACT - 8802 | Closed | 29/11
2024 | November |  | 2024-11-28 | 5.15pm | Email | L2 | Location of the Cobb Highway Camp | Unavoidable | A near neighbour to the Cobb Highway Camp has been sent a notification advising the Cobb Highway camp will open next week. The near neighbour is unhappy about the location of the camp, lighting and the number of people staying at the camp. | The near neighbour has advised us not to contact her until the camp is closed. |  |  | ACT-87869 | Closed | 2024-11-28
2024 | December |  | 2nd Dec | 11am | Meeting | L5 | Property access | Avoidable | Land Access Officer informed of a verbal exchange between H189 and PEC worker after access was denied given weather conditions. A complaint was escalated to local authorities to undertake investigation. | The incident was communicated to the Construction team and lodged in PEC's complaint system. The construction program to resume when weather conditions are more favourable. Onsite meeting with Construction PM scheduled in New Year to discuss incident and detirmine access protocols. |  |  | ACT-88493 | Closed | 2024-12-13
2024 | December |  | 5th Dec | 8am | Phone call | L2 | Gates left open | Avoidable | Land Access Officer received phone call from L/H representative regarding gates left open between H075 and H081. | Land Access Officer acknowledged complaint and advised that 'open/close' gate signs will be installed and construction. On 11/12/2024 Land Access officer installed nine high visable gates signs on the property and L/H satisified with the initiative |  |  | ACT-88938 | Closed | 2024-12-13
2024 | December |  | 2024-12-09 | Midday | Email | L2 | PEC worker behaviour. | Avoidable | A member of the public witnessed a PEC employee in uniform and during working hours drinking at Coleambally pub in late November. | The Project Construction team has investigated this matter and spoken to the employee involved on several occassions. IVMS has been used to locate the worker's movements. |  |  | ACT-89317 | Closed | 2024-12-19
2024 | December |  | 11th Dec | After hours | Phone call | L5 | Stock incident | Unavoidable | Land Access Officer advised today that he received a call yesterday evening from L/H181 regarding two perished head of cattle. It is alleged that this incident was a result of the cattle eating loose plastic that had been left on the PEC work site. L/H seeking compensation. | Land Access Officer acknowledged the complaint and advised the Construction Team to investigate the incident. 20/12 - L/H agreed to meet with PEC team on-site in the new year where a re-imbursement will be negotiiated. Construction team re-iterating site protocols in pre-starts. |  |  | ACT-89653 | Closed | 20th Dec
2024 | December |  | 13th Dec | After hours (8pm) | Phone call | L2 | Gate installation | Avoidable | Land Access Officer received a call from L/H069 regarding the installation of a gate on the easement that was not in line previous discussions and without consultation. | Land Access Officer met with the Construction team to raise the matter and investigate the issue. An onsite meeting took place with L/H where a decision was made to relocate the gate position to the satisfaction of L/H that would also meet project requirements. |  |  | ACT-89651 | Closed | 17th Dec
2024 | December |  | 2024-12-13 | 12.30pm | Email | L2 | Bio-security | Avoidable | A representative of H090 emailed the PEC Land Access Officer advising spiny burr presence along access tracks and tower pad edges. Also raised the issue of still awaiting installation of brush down bays. | Land Access Manager called L/H representative and lodged issue with the Construction team to explore mitigations. 20/12 - PEC team agreed to a herbicide spraying program. Construction Team agreed to install temporary brushdown bays in the New Year. L/H's Operation Manager please satisified with the response. |  |  | ACT- 89652 | Closed | 20th Dec
2024 | December |  | 2024-12-16 | 7.20am | Phone call | L5 | Out of hours property access | Avoidable | Land Access Officer spoke with L/H176 to regarding the PEC construction crew performing works on Sunday15th, which is outside of agreed working hours.The L/H had to subsequently interrupt his spraying program for the safety of staff and now seeking reimbursement of associated costs. | The Land Access Officer lodged the issue in an incident management system and raised with the Construction Team for investigation. 20/12 - The Construction Team agreed to conduct a Land Access induction program to remind work crews of property access protocols. L/H agreed to meet with Land Access Officer in the new year when he has time to discuss reimbursement costs. L/H satifisfied with the agreed approach. |  |  | ACT-89757 | Closed | 20th Dec
2024 | December |  | 2024-12-28 | 3pm | Website | L5 | Stock welfare, project communication and track condition on the property | Avoidable | L/H188 lodged a complaint via the project's community website from raising easment and construction issues. | The complaint was forwarded to the contactor to assist with the investigation upon the project re-opening in the New Year. The Construction team agreed to rectify wheel track marks at the same time equipment is on site to construct and access track. Other issues raised in the orginal complaint and now being managed with the L/H via the the proponent's legal team under a seperate resolution process. |  |  | ACT-90271 | Closed | 15th Jan
2025 | January |  | 2025-01-06 | 9.41am | Facebook | L5 | Access gate locked preventing farmer from managing stock. | Avoidable | LH141 posted facebook a video expressing his dissatisfaction that a lock had been placed on gates which were in place prior to the construction. The padlock had to be removed to allow livestock to enter the property. He also drew attention to gates which were installed as part of the construction which were not locked. | The Land Access team acknowledged the complaint with the L/H and agreed to remove the padlock and leave the gate latched, but not locked. Construction Team notified that the gate is to remain closed and latched at all times. |  |  | ACT-90318 | Closed | 2025-07-01
2025 | January |  | 2025-01-08 | 1.35pm | Phone call | L5 | Accessing property without vehicle inspection | Avoidable | Land Access Officer received a call from L/H134 regarding a construction vehicle entering the site without a bio-security inspection. The PEC worker was asked to leave and the gate locked until a meeting takes place with the Land Access Team. | Complaint acknowledged. The Land Access team notfied the Construction team and re-iterated bio security protocols on the property. The proposent's Land Access team met with the L/H and agreed to new mitigations including a dedicated construction supervisor responsible for vehicle inspections. Additionally, a new protocol was agreed to where vehicles are not to travel between the boundaries of H134 and H136 without prior communication via the construction supervisors. |  |  | ACT-91043 | Closed | 18/1/24
2025 | January |  | 2025-01-10 | 8.47am | Email | L5 | Accessing the property without providing vehicle bio-security log-in sheets | Avoidable | L/H 196 issued a complaint indicating that the project had not provided copies of the vehicle log-in sheets as part of the property's bio-security protocols. (requested 11/12). Consequently, the L/H has locked the gate until a response and supply of log-in sheets are provided. | The Land Access Officer acknowledged the complaint and actioned the request by suppliying copies of the log-in sheets from the Construction Team. A meeting is to be scheduled with the L/H when he returns from Leave to discuss his administration requests going forward and confirm the bio-secuirty protocols in place. |  |  | ACT-91558 | Closed | 24/1/25
2025 | January |  | 12th Jan | 9.10am | Phone call | L5 | Accessing property outside agreed working hours | Avoidable | Land Access Officer recieved a phone call from L/H176 on Sunday morning advising he saw a PEC vehicle accessing his property. L/H considers this entry a breach of agreed access conditions and unlawful. L/H advised the police of entry. | The Land Access Officer immediatley notified the Construction team. The Construction Manager then instructed the worker to exit the property, and spoke with the police to explain project activities and access requirements to the property. The GPS mapping has been updated in the IVMS software to ensure correct routes are taken when accessing the property. The Construction workforce to be reminded at pre-starts of land access requirements A meeting will be held with the L/H to discuss and confirm access protocols and the permits currently in place. . |  |  | ACT-91312 | Closed | 24/01/25
2025 | January |  | 17th Jan | 3.45pm | Email | L5 | Poor worker behaviour in public | Avoidable | The Engagement Team recieved a call centre complaint lodged on 16th of January from a community member who witnessed a construction worker acting indecently in public. The community member recorded the incident and has provided licence plate details of the vehicle. | The incident was investigated and verified worker involved. The worker has been disciplined and an apology has been put forward by the Constrcution Manager and worker to the community member. |  |  | ACT-91607 | Closed | 31/1/25
2025 | January |  | 2025-01-31 | 10.45am | Call | L2 | Survey flagging and plastic litter | Avoidable | Land Access Officer received a complaint from L/H082 regarding heritage and environmental survey flagging that has fallen over onto the ground within his paddock. He also indicated that plastic has blown across into paddocks from the project site and could pose a health risk to his livestock. | The complaint was acknowleged by the Land Access Officer. The Environment Team sent a crew to collect the plastics and rectified the survey flagging. Alternative fencing for survey areas being considered. |  |  | ACT-92556 | Closed | 2025-02-07
2025 | February |  | 2025-02-09 | 10.30am | Call | L5 | Out of Hours Work activity on a Sensitive Receiver's property at Uranquinty. | Unavoidable | A sensitive receiver on Line 5 phoned to ask if construction work would cease on their property as they are listed as sensitive receivers with no out of hours work permitted. | The complaint was acknowleged by a site supervisor and work was immediately stopped. A check of the permit showed the caller was a sensitive reveiver. The construction team had not referred back to their documentation correctly. |  |  | ACT-93490 | Closed | 2025-02-09
2025 | February |  | 13/2 |  | Email | L5 | PEC vehicle safety | Avoidable | On 4th Dec 2024, L/H196 advised PEC Land Access Officer of a safety incident - PEC HV moving east on Oxley Bridge Rd was on the wrong side of the road while travelling around a bend. L/H was forced to drive off to the side of the road. | The incident was lodged in the project's safety management system. The investigation concluded that the road is suitable for single carriage only, and does not have adequate width for two vehicles to pass in opposite directions at the same time - without the left hand side tyres of the passing vehicles being placed into the gravel section of the road while passing each other. IVMS records indicate that the driver of HV was not speeding, showing a maximum speed of 15km/hr. A copy of the investigation findings were emailed to the L/H. |  |  |  | Closed | 13/2
2025 | February |  | 13/2 | 4pm | Email | L5 | Vehicles traffic and dust | Avoidable | A Land Access Officer on Humelink received a communication from a L/H advising of an incident whilst travelling on Boiling Down Road. The incident occurred near the PEC substation site at Wagga Wagga and involved three dark vehicles driving towards him with little line of sight due to dust. The Land Access officer then advised PEC Engagement on 7th Feb inquiring if there are any dust mitigations in place. | The Incident was investigated by the PEC where it was concluded the vehicles were not PEC related. Boiling Down Road is a Government controlled, unsealed Road. During the day this road is used by members of the public, along with numerous heavy vehicles utilising the nearby refuse depot. PEC will notify the council of the issue. |  |  |  | Closed | 13/2
2025 | February |  | 15/2 | 2.25pm | SMS | Wagga Wagga | Gate left unlocked | Avoidable | L/H210 sent SMS to Land Access Officer advising the gate off Redbank Rd at structure 4 was left unlocked - potentially exposing his cattle to the public. The L/H advised that these gates are to be locked at the end of each day. | Construction Team placed a lock on the gate and advised that a Site Supervisor will be made responsible to lock the gate after each work shift. |  |  | ACT-93949 | Closed | 24/2
| February |  | 21/2 | 1.12pm | Email | L5 - Lockhart | Oversized load, unsafe driving, no signage and escort | Avoidable | A local landholder (not on PEC) claims he was forced off the road on the intersection of Country Boundary Road and Slys Lane Milbrulong by a subcontractor vehicle on Project EnergyConnect. A hose was seen hanging from one side of the vehicle. The unrestrained and oversized load also had no signage, flagging and or escort. | An investigation was carried out indicating that the subcontractor's vehicle was complying with safety standards and no unsafe behaviour was exhibitied. |  |  | ACT-94314 | Closed | 3/3
2025 | February |  | 21/2 | 1.54pm | Email | L5 - Lockhart | Project EnergyConnect crew didn't close property boundary fence gate allowing stock to wander away from the property. | Avoidable | Landholder 096 property boundary fence not being closed, the landholder's bull is missing. The landholder advised this was the second time his gates had been left open. In the previous incident, ten days ago, the landholder had to muster about 90 sheep back to his adjoining neighbour's property. | Construction team was advised, and an apology was given to the landholder. Issue raised at prestart meeting on Monday, 24 February 2025. The bull has not been located at this stage. |  |  | ACT-94315 | Closed | 5/3
2025 | February |  | 27/2 | 10pm | Email | L5 - Cullivel | Bio-security and loose items on property posing risk | Avoidable | Land Access team reported a complaint issued by H134. Issues include potential foreign soil and seed being introduced to the property on stringing equipment, plastic waste left on site, survey pegs left on the ground posing risk to L/H machinery, and steel star pickets also posing safety risk. | A full site clean-up, including the easement, was completed. The pull winch and break winch were adjusted to prevent the spread of weed seeds or vegetation between neighbouring properties. A ground cover sheet was placed under the winch to capture and dispose of any foreign material. |  |  | ACT-95425 | Closed | 7/3
2025 | March |  | 2025-03-05 | 3.20pm | Phone | L5 - The Rock | Dust on Hanging Rock Road | Avoidable | A near neighbour to the project claims Project EnergyConnect vehicles travelling at 100kms an hour is causing dust issues to his property. The neighbour has asked if drivers could slow down. | Construction team notified and the team has been advised at Prestart to slow down. Construction has also advised they will use a water truck regularly along this unsealed road to help reduce the impact of dust. |  |  | ACT-95769 | Closed | 18/03
2025 | March |  | 2025-03-07 | 4.55pm | Email | L2- Boorooban | L/H consultation and heritage concerns | Avoidable | H081 emailed concerns via legal representative regarding consultation, information requested not being provided and heritage concerns about vegetation clearing. | Construction and Land Access team met with L/H to discuss converns. Solution in place regarding construction notifcations, protocols of tree felling, and access requirments. Commercial Team addressing formal correspondence. |  |  | ACT-96543 | Closed | 18/3
2025 | March |  | 2025-03-10 | 3.20pm | Email | L2 - Booroorban | Road condition and poor driver behaviour | Avoidable | The complainant emailed her concerns about Booroorban Tchelery Road, especially the grid crossings. The caller also raised issues around poor driver behaviour with crews not slowing down and leaving enough room for other vehicles to pass. | Construction team alerted the Council who will be undertaking grid repairs. Safety alert issued to construction teams regarding driver behaviour, and crews at L2 advised of driving protocols including the area raised in the complaint. |  |  | ACT-96303 | Closed | 18/3
2025 | March |  | 2025-03-19 | 1.50pm | Text | L2 - Booroorban | Poor driver behaviour | Avoidable | L/H069 texted PEC Engagament team complaining about the driving behaviour of a water truck operator on Booroorban Tchelery Road. | Safety Team identified the driver and highlighted expected driving protocols on the local roads. The Safety team issued pre-start messages to the Construction team. L/H contacted and he stated he has already seen an improvement in driving behaviour. |  |  | ACT-97006 | Closed | 28/3
2025 | March |  | 2025-03-24 | 10.25am | Phone call | L5 - Uranquinty | Vehicle hygiene | Avoidable | L/H 189 called the Land Access Officer advising that a vehicle was denied entry to the property as it was not complied with the come clean, go clean procedure. L/H requested a meeting to discuss the bio-security protocol. | Land Access and Construction teams met with L/H on the 27/3 to discuss bio-security resourcing and inspection protocols. The Construction Team agreed to appoint new personnel to manage vehicle inspections. The L/H was satisfied with the suggested action. |  |  | ACT-97242 | Closed | 27/3
2025 | March |  | 2025-03-27 | 3pm | Phone call | L2 - Balranald | Construction and land access issues | Avoidable | L/H50 issued a complaint to a PEC Land Access Manager regarding range of construction and land access issues caused by the project. Examples include disused survey pegs remaining on site, damage caused to equipment by the pegs, access track construction, timber clearing instructions, rubbish left on site. | Transgrid and Elecnor met with the landholder and raised a series of commitments and mitigations to address the outstanding issues. Transgrid will manage the Lease Negotiations separately with the L/H. |  |  | ACT-97601 | Closed | 2025-04-01
2025 | April |  | 2025-04-01 | 10.09pm | Email | Not on the alignment - Southeastern freeway near Adelaide | Driver safety | Avoidable | A member of the community emailed the team about the discourteous and intimidating behaviour of an Elecnor driver. The rego and vehicle number have been supplied. | The investigation revealed that this was not a PEC vehicle. The complaint was advised that the matter was handed over to Elecnor's H&S Australian team where the driver will be disciplined. |  |  | ACT-98326 | Closed | 2025-04-07
2025 | April |  | 2025-04-01 | 9.57pm | Email | L2 - Coleambally | Off- easement access and Spiny Burr presence | Avoidable | L/H090 emailed the Land Access Team advising that a PEC-related vehicle had travelled off easement and entered a no-go constrution zone near towers 40-41, and that the presence of Spiny Bur throughout the paddock is a breach of bio-security protocols. | The Land Access team advised the team who commisisoned the supplier of the correct property entry protocols. A spraying program is scheduled to address weed issues. |  |  | ACT-99039 | Closed | 2025-04-08
2025 | April |  | 2025-04-03 | 9am | Text | L2 | Gates not locked | Avoidable | LH62 issued a complaint regarding a gate left unlocked. L/H seeking reimbursement costs for travel and time to rectify. | The Construction Team have agreed to several new mitgations including the gate will be locked at 5pm each day with photographic evidence to be provided. A sign has be placed at the gate and another toolbox has been implemented to all personnel. |  |  | ACT-99059 | Closed | 2025-04-08
2025 | April |  | 2025-04-03 | 7.40am | Call | L2 | Vehicle travelling too slowly | Avoidable | A community member notified the Land Access Officer issuing a complaint that he encountered a PEC vehicle was travelling too slowly on Tchelery Road causing the driver to be late for an appointment. | The community member was advised that the vehicle operator was travelling carefully on a single carriage road. The Construction team was notifed and will issue pre-start messages reminding the workforce of courteous driving behaviour when travelling on local roads. |  |  | ACT-98583 | Closed | 2025-04-03
2025 | April |  | 2025-04-10 | 8am | Meeting | L5 - Uranquinty | Construction litter and worker behaviour | Avoidable | L/H189 190 issued a complaint to the Land Access Manager regarding finding littered cigarette butts on the property left by PEC construction workers. Additionally, the L/H observed a PEC employee attempt to kick the door of a slow moving vehicle passing on hanging Rock Rd | Construction crews reminded of site access protocols. Staff were provided butt bins for vehicles and butt belts for staff. L/H happy with outcome. |  |  | ACT-99733 | Closed | 2025-04-16
2025 | April |  | 2025-04-11 | 3.30pm | Phone call | L5 - Urana | Gates being left open | Avoidable | LH104 issued a complaint regarding the access gates being continual left open by PEC work crews - posing a risk of an accident should stock walk onto Coonong Road. | The Construction Team advised the crew working at that location of the correct access protocols. Reminders at the workforce prestart meeting were issued the following day. |  |  | ACT-99729 | Closed | 2025-04-17
2025 | April |  | 2025-04-11 | 3.30pm | Phone call | L5 | Driving behaviour | Avoidable | A community member 'droving' cattle along the Newell Highway reported to PEC workers that a PEC sub-contractor truck driver displayed discourteous behaviour when travelling through the walking cattle herd. | The Land Access Officer met with the community member and apologised on behalf of the project. The Manager of the driver had a one-on-one discussion where the behaviour was addressed. |  |  | ACT-99736 | Closed | 2025-04-16
2025 | April |  | 2025-04-20 | 12.15pm | SMS | L5 - Tootool | Out of hours access | Avoidable | H176 advised the PEC Land Access Officer of a vehicle entering the property on Sunday without prior access approval. | The Construction Team was notified and the vehicle operator was asked to exit the property. EA installed signs on L/H property communicating access hours. EA contacted L/H who was comfortable with mitigation. |  |  | ACT-100074 | Closed | 2025-04-30
2025 | April |  | 2025-04-23 | 8.15am | SMS | L5 - Uranquinty | Biosecurity inspection | Avoidable | L/H190 issued a complaint in relation to khaki seeds found on a PEC vehicle attempting to enter the property. | The vechicle was cleaned and the seeds bagged. Further communication issued to construction teams - recruitment of dedicated vehicle inspectors in progress. |  |  | ACT-100193 | Closed | 2025-04-24
2025 | April |  | 2025-04-23 | 12.30pm | Call | L5 - Urana | Road condition | Avoidable | H118 issued a complaint to the PEC Land Access Officer about the deteriorating condition of roads within his local area. | The Council Interface and Construction Teams were notified. Graders and water carts deployed to the identified roads to address the issues. |  |  | ACT-100241 | Closed | 2025-05-02
2025 | April |  | 2025-04-24 | 7.15am | Call | L5 - Uranquinty | Biosecurity inspection | Avoidable | L/H190 issued a complaint in relation to khaki seeds found on a PEC bus and workforce footwear while attempting to enter the property. The vehicle was turned away. | The Construction Team implemented new mitigations address cleaning protocols of the bus prior to property entry. L/H happy with this action. |  |  | ACT-100284 | Closed | 2025-04-24
2025 | April |  | 2025-04-28 | 7.45am | Call | L5 - Tootool | Gates left open | Avoidable | Land Access Officer received a phone call from the project team that gates between towers 84/85 had been locked by L/H177. The landholder was frustrated that gate was left open as it presents a risk to the welfare of his stock should they wander into the adjoining paddock. | High visibility closure signs have been installed on the access gates and reminders provided to crews. Landholder satisfied mitigations put in place and lock removed. |  |  | ACT-100355 | Closed | 2025-04-28
2025 | May |  | 2025-05-01 | 1.00 PM | Email | Lockhart | Speeding vehicle in the community | Avoidable | A community member reported a speeding vehicle on Lockhart-Boree Creek Road. The community member also raised concerns about trees blocking visibility near the railway signs, which have been reported to Lockhart Shire Council. | Construction team reminded about the hazards of this section of road including the blind corner, local speed limits and its narrow width. The Safety team are planning a workforce campaign for safe driving protocols. |  |  | ACT-101248 | Closed | 2025-05-07
2025 | May |  | 2025-05-05 | 8:15 | Call | L5 | Biosecurity breaches, Lack of lookahead, Vehicle hygiene non-compliance, No supervisor presence | Avoidable | L/H189–190 reported non-compliance with agreed property biosecurity protocols referencing vehicle inspections, hygiene sheets and property entry point. The landholder locked the entry property gates. | The PEC Land Access and Construction Team met with the the landholder and agreed to improved mitigations including the training of dedicated vehicle inspection staff, supplying of weekly construction schedules and the installation of new lock on an internal gate, and reminders to the workforce of biosecuity protocols. |  |  | ACT-101488 | Closed | 2025-05-08
2025 | May |  | 2025-05-06 | 10:00am | In person | L2 | Damaged fencing | Avoidable | Construction stringing activity caused damage to an internal fence on L/H 046. Landholder alleges this potentially allowed Merino stud sheep to mix with Dorper sheep in adjoining paddock. | Fence was fixed the same day by construction. The team is reviewed stringing approach on this property The PEC Land Access Manager met with L/H and agreed on mitigations to manage stock. |  |  | ACT-101646 | Closed | 2025-05-15
2025 | May |  | 2025-05-15 | 12:28 | Email | L2 | PEC vehicle not sharing the road | Avoidable | A community member advised the PEC Engagement Team that a driver of a contract cement truck caused a passenger vehicle to veer off Booroorban Tchlerey Road, and that there have been other reports of these trucks displaying dangerous road use. | Road safety protocols reinforced with the workforce, included targeted conversations with contract cement truck operators. Incident was lodged in Safety Management system. |  |  | ACT-102773 | Closed | 2025-05-28
2025 | May | 45794 | 2025-05-17 | 11.40am | Email | L5 - Tootool | Gate closure | Avoidable | H176 notified the Land Access Officer that his sheep had been boxed in a paddock due to the PEC construction crew not closing an internal property gate correctly. | Construction Team notified and the gate was closed and locked correctly the same day. Internal gate closure protocols reinforced with the work crew and reminders included in morning pre-start briefing. |  |  | ACT-102946 | Closed | 2025-05-21
2025 | June |  | 2025-06-23 | 8.00am | Phone call | L5 - Uranquinty | Gate closure | Avoidable | L/H191 called the Land Access Officer advising that a PEC survey vehicle had travelled through his property leaving a gate open, which resulted in stock being boxed. | The responsible contractor was reminded of gate protocols. Additional reminders communicated at pre-start meetings the followng monring. EA installed open and close signs. |  |  | ACT-107369 | Closed | 2025-06-23
2025 | July |  | 2025-07-02 | 5.25pm | Email | L2 | Employee interaction with Griffith LALC | Avoidable | A complaint regarding employee conduct was received by Transgrid via email, following a phone conversation between a representative of Griffith Local Aboriginal Land Council (LALC) and a member of the PEC Engagement Team. | The complaint was acknowledged, and an internal investigation undertaken.Transgrid povided a formal response to Griffith LALC, and no disciplinary action issued to the PEC Engagemeng Team member. |  |  | ACT- 110956 | Closed | 2025-07-10
2025 | July |  | 2025-07-08 | 4.22pm | Email | L2 | Mobile phone coverage | Avoidable | A complaint regarding the impact on mobile phone coverage since the increase in construction activities in the Dinawan area was emailed to Transgrid. The complainant is seeking reimbursement for the purchase of Starlink. | The complaint was acknowledged by Transgrid, who will remain in contact with the community member while inquiries are undertaken with EnergyCo. Elecnor provided Transgrid with data and an overview of workforce mobile phone use patterns and Starlink activity, which was used to inform the feedback to the community member |  |  | ACT-110765 | Closed | 2025-07-10
2025 | July |  | 2025-07-09 | 6.00pm | Phone | L5 - Rowan | Trees removed and brake & winch equipment moboilised without L/H knowledge. | Avoidable | L/H205 contacted EA Land & Access Officer to complain that two large trees have been removed from his property. The L/H also advised he had no knowledge of brake and winch equipment being moboilised on his property. | The Land Acces Team organised to meet with the L/H to discuss the stringing schedule, once supplied by the Construction Team and L/H confrims availability. The complaint has been closed and a commitment raised to discuss mitigations with the landholder. |  |  | ACT-110857 | Closed | 2025-07-15
2025 | July |  | 2025-07-16 | 10.00am | Phone | L5 - Lockhart | Generator broken down | Avoidable | H165 contacted EA Land & Access Officer to inform that the generator had broken down and there was no power to the house. | The generator was refulled by the L/H. Enercon was called to site to investigate the issue. The Landholder was satisfied that the complaint was actioned. |  |  | ACT-111608 | Closed | 2025-07-17
2025 | July |  | 2025-07-19 | 7.52pm | Email | L2 - Booroorban | EA & TG using stock grid and not designated gates | Avoidable | H069 email the PEC Construction and Land Access Team Managers advising that PEC vehicles had been accessing the easement via the stock grid adjacent to the designated gates. | The Construction Team acknowledged the complaint with the L/H and advised him there will be follow-up with the reported vehicle operators and the matter will be discussed at prestart meetings. |  |  | ACT-112110 | Closed | 2025-07-28
2025 | July |  | 2025-07-21 | 8.41am | Email | L5 - Rowan | Allegation by community member regarding PEC employee conduct | Avoidable | The Transgrid community inbox received an email from a near-neighbour to the PEC alignment complaining about the conduct of a Community Liaison Officer | Transgrid investigated the circumstances of the complaint and liaised with the community member on the outcome of their findings. |  |  | ACT-112191 | Closed | 2025-07-30
2025 | July |  | 2025-07-28 | 2.15pm | Phone call | L5 - Rowan | Gate left open | Avoidable | H209 called PEC Land Access Officer advising that a gate had been left open and sheep had walked into neighbouring property. L/H mustered sheep back into his property and requested that this gate to be always closed after entry. | The Land Access Officer acknowledged the complaint and advised the L/H the Construction team were notified. A gate sign was installed to communicate that it should be left in the closed position. The L/H was happy with this mitigation. |  |  | ACT-112889 | Closed | 2025-07-28
2025 | July |  | 2025-07-31 | 9.56am | Phone call | L5 - Tootool | Local road condition | Avoidable | A community member residing in Tootool lodged a complaint with Trangrid’s community call centre regarding the impact of construction vehicles on the condition of Hendersons Road. | Transgrid acknowledged the community member's complaint. The PEC Engagement Manager then advised the community member that the Construction Team is scheduled to undertake repairs to Henderson Road on the 7th of August. The community member was satisfied with the quick resolution of the complaint and the attendance to the repairs. |  |  | ACT-113287 | Closed with mitigation | 2025-08-04
2025 | August |  | 2025-08-08 | 3.10pm | Phone call | L5 | Postponing of cultural awareness training | Avoidable | A First Nations business that was booked to provide cultural awareness training at two of the project's camps issued a complaint following the postponing of the sessions. | The Complaint was acknowledged by the project's Communications and Engagement Lead. A follow-up call was made to apologise for the miscommunication and explain the reason for postponing. The intention to continue engagement with the organisation and its Elders after further planning was reaffirmed, and the Elders expressed appreciation for the clarification. |  |  | ACT-114556 | Closed with a commitment | 2025-08-11
2025 | August |  | 2025-08-28 | 10.30am | Phone | L5 Bundure | Gate left open | Avoidable | H094 called the PEC Land Access Officer reporting gates left open onto Thurrowa Rd and Bundure Rd, raising risks to property and livestock. | The Land Access Officer acknowledged the complaint and then attended the property, closed the gates, and confirmed the issue was resolved. The Construction team were notified and reminded of gate protocols. The landholder has been invited to meet and discuss further if needed. |  |  | ACT-117634 | Closed with mitigation | 2025-08-28
2025 | August |  | 2025-08-28 | 10.45am | Phone | L5 Bundure | Road condition | Avoidable | H095 reported the poor condition of Bundure Road, raising safety concerns and requesting repairs. | The Land Access Officer acknowledged the complaint. advised the landholder that project crews will be undertaking repairs to Bundure and surrounding roads with works commencing 15 Sept. |  |  | ACT-117646 | Closed with mitigation | 2025-09-03
2025 | August |  | 2025-08-30 | 7.15am | Phone | L5 - Uranqunity | Unauthorised acces | Unavoidable | A community member living near to the PEC corridor called the community 1800 number advising that an Essential Energy worker had accessed her property without notification and begun setting up works. | The Community Stakeholder Manager advised the community member that Essential Energy is not a contractor to Elecnor, and that the project team only undertakes works within the PEC easement and approved hours. The community member was referred to Essential Energy for further information about the works. |  |  | ACT-117864 | Closed with a response | 2025-08-30
2025 | September |  | 2025-09-07 | 2.00pm | Meeting | L5 - Uranqunity | Biosecurity | Avoidable | Landholder H195 reported that a project vehicle entered their property without complying equipment and vehicle cleaning procedures.. | The Land Access Officer acknowledged the complaint and inspected the property. The driver was reminded of vehicle hygiene requirements and directed to remove the vehicle. The construction team has issued fobs for Wagga based operators to use at car wash facility |  |  | ACT-119118 | Closed with mitigation | 2025-09-12
2025 | September |  | 2025-09-21 | 8.50am | Phone | L5 - Uranquinty | Subcontractor accessing private property adjacent to the project. | Avoidable | A community member living next to the project easement reported that a subcontractor security guard working for Elecnor entered their property without authority. | The residents were advised that the security guard mistakenly entered their driveway, believing it was access to the project easement. The security company has been instructed not to enter the property, and a ‘No Entry’ sign will be installed at the front gate. |  |  | ACT-120509 | Closed with mitigation | 2025-10-01
2025 | September |  | 2025-09-22 | 8.34am | Phone | L5 - Rowan | Flagging and animal welfare | Avoidable | Landholder H205 reported that a stud ewe became entangled in environmental flagging and perished after a period of time. The landholder expressed concern for animal welfare and has moved sheep out of paddocks where flagging is currently in place. | The Land Access Officer acknowledged the complaint. The carcass and flagging were removed, an apology was issued, and the landholder will be reimbursed for costs associated with the ewe. Additional mitigations include prompt removal of environmental flagging after tower stringing and revised flag-tying techniques to improve durability and reduce future risks. |  |  | ACT-121414 | Closed with mitigation | 2025-09-29
2025 | September |  | 2025-09-23 | 3pm | Letter / email | L2 - Booroorban | Local road condition | Avoidable | Elecnor received a letter from the Office of the Australian Energy Infrastructure Commissioner (AEIC) raising community concerns regarding the condition and safety of several local roads in the Hay and Edward River regions, with specific reference to Booroorban Tchelery Road, Willurah Road, and Carrathool Road. | The Engagement Manager acknowledged receipt of the letter. Elecnor provided a response outlining the Project’s obligations under the Infrastructure Approval and the road maintenance activities underway with councils, including the ongoing dilapidation survey program. Elecnor also extended an invitation for continued engagement with the AEIC. |  |  | ACT-121451 | Closed | 2025-09-30
2025 | September |  | 2025-09-25 | 11.30am | Phone call | L5 - Tootool | Unapproved vehicle access | Avoidable | Landholder H176 contacted the PEC Land Access Officer to report that three project-related vehicles entered their driveway without authorisation. | The complaint was acknowledged with the landholder. Investigation confirmed the crew were new to this section of the project and had mistakenly entered via an incorrect access point. The crew apologised directly to the landholder. Updates have been made to the in-vehicle monitoring system (IVMS) to activate exclusion boundary alarms on contractor vehicles, and additional reminders on correct entry points have been reinforced at pre-shift safety briefings. |  |  | ACT-121165 | Closed with mitigation | 2025-09-29
2025 | September |  | 2025-09-24 | 10am | Meeting | L5 - Uranquinty | Electrical generator issue | Avoidable | The PEC Engagement Manager and Engagement Lead met with the local resident as part of a follow-up to a previous complaint. During the meeting, the community member raised several concerns about the project, including a project-related generator that appeared to be faulty and had caused multiple electrical outages on the property resulting in damage to the owner's fridge. | The subcontractor attended the property and repaired the generator. The Project’s Engagement Team investigated the additional concerns raised by the community member and confirmed that signage will be installed at the property’s entry gate. All crews have been reminded that access to the easement is via the neighbouring property |  |  | ACT-121450 | Closed with mitigation | 2025-10-03
2025 | September |  | 2025-09-30 | 7.55am | Email | L5 - Uranqunity | Electrical generator issue | Avoidable | The Energy and Water Ombudsman (EWON) issued correspondence to Transgrid's community inbox regarding a community complaint about a faulty generator supplied during an Essential Energy outage, undertaken to facilitate project stringing works approximately 500m from the property. | Transgrid acknowledged the complaint and made a commitment to respond to the community member and EWON within the required timeframe with the outcome of its investigation.. |  |  | ACT-122148 | Closed with a comittment | 2025-09-30
2025 | October |  | 2025-10-01 | 1.30am | Email | L2- Griffith | Engagement protocols with Griffith Local Aboriginal Land Council | Uavoidable | Transgrid received an email from the CEO of the Griffith Local Aboriginal Land Council raising concerns about Transgrid's local aboriginal engagement protocols and the opportunities to participate in EnergyConnect. | The Transgrid Engagement Team acknowledged the complaint and have committed to an in-person meeting to discuss the concerns highlighted in the correspondence. |  |  | ACT-122662 | Closed with a comittment | 2025-10-09
2025 | October |  | 2025-10-02 | 12.30pm | Phone call | L5 - Uranquinty | Electrical generator issue | Avoidable | H189 contacted the PEC Land Access Officer to report that the Enacon generator is tripping. | Enacon sent a technician to rectify the issue and has arranged an electrical subcontractor located in Wagga to be on call if required. |  |  | ACT-122742 | Closed with mitigation | 2025-10-02
2025 | October |  | 2025-10-17 | 8am | In -person | L5 - Uranqunity | Worker behaviour | Avoidable | A local landowner, H189, reported to the PEC Land Access Officer that a traffic controller subcontracted to the project verbally swore at her while she was travelling on a local road, alleging she was driving too fast. | The PEC Land Access Officer acknowledged the complaint and apologised to the landholder on behalf of the project. The Construction Team was notified and an investigation into the incident is underway. A commitment was made with the Landholder that the outcome will be provided following the investigation. |  |  | ACT-124543 | Closed with a commitment | 2025-10-28
2025 | October |  | 2025-10-23 | 3pm | Phone | L5 - The Rock | Excessive dust | Avoidable | A community member phoned the project 1800 number to complain about excessive dust at her home caused by project vehicles using an unsealed road at The Rock. | The Community Engagement Lead acknowledged the complaint. The Construction Team sent a water truck to the location to undertake dust supression, and 'no go' signage has been placed either end of the unsealed road. The workforce has been briefed to not to use this road. The community member was advised and was happy with the steps taken by the project. |  |  | Act-124954 | Closed with mitigation | 2025-10-27
2025 | October |  | 2025-10-27 | 4.55pm | Phone | L5 Bundure | Gates left open | Avoidable | H094 reported to the PEC Land & Access Officer that gates were left open at an easement access point, posing a risk to livestock. | Mitigations include the landowner installing a lock on the boundary gate and each crew nominating a person to confirm gate closure with the Construction Manager at the end of each shift. Disciplinary action will apply if the issue recurs. The landowner has confirmed satisfaction with the actions taken. |  |  | ACT-125394 | Closed with mitigation | 2025-10-31
2025 | November |  | 2025-11-05 | 8.00am | Phone | L5 - Urana | Road condition | Avoidable | H124 contacted the PEC Land Access Officer expressing concern that project vehicles were using recently repaired unsealed roads during wet conditions, potentially causing renewed deterioration. | The Land Access Officer acknowledged the concern and referred it to the Construction team. The Construction team confirmed maintenance works are underway in the area and will advise crews to use sealed roads where practicable to minimise impacts on unsealed sections. |  |  | ACT-127205 | Closed with mitigation | 2025-11-06
2025 | November |  | 2025-11-11 | 8.00am | Phone | L5 - Urana | Gates left open | Avoidable | H104 reported to the PEC Land Access Officer that gates on his property were left open by project personnel, allowing livestock to escape into adjoining paddocks. The landholder noted that mustering the animals back is time-consuming and requested a plan from the project team to prevent recurrence. | A reminder was sent to all stringing crews of Elecnor’s property access policy. Additionally Stringing Supervisors were directed to immediately inspect all property gates between towers T236 and T277. Going forward, a dedicated team member has been assigned to patrol the area throughout the day to enforce gate-closure requirements and ensure no loose materials or debris are left behind. |  |  | ACT-127756 | Closed with mitigation | 2025-11-11
2025 | November |  | 2025-11-17 | 8.00am | Email | L5 - Uranqunity | Local road condition | Avoidable | A Uranquinty resident contacted the Transgrid community line with concerns about the condition of repair works on Paynes Road and South Boundary Road, as well as dust impacts by vehicles using the roads. | The complaint was acknowledged with the resident. The Construction Team confirmed that the project had not undertaken any works at this location. However, after liaising with Wagga City Council, they agreed to dispatch a maintenance crew (weather permitting) to commence works from Wednesday, 26 November. The community member was informed and appreciated the update. |  |  | ACT-128353 | Closed with mitigation | 2025-11-24
2025 | November |  | 2025-11-25 | 9.05am | Phone call | L5 - Uranqunity | Gate left open | Avoidable | LH191 reported that a property gate was left open, allowing cattle to enter his crop and cause damage. | The Land & Access Officer acknowledged the complaint and notified the Construction team to investigate. A meeting held with the landholder to assess the damage and outline measures to prevent a recurrence. The investigation revealed that it was a fence that had been cut and it has now been subsequently repaired. The Landholder to be reimbursed for damages to cropping after harvest. |  |  | ACT-130792 | Closed with mitigation | 2025-11-28
2025 | December |  | 2025-12-04 | 8.00am | Phone call | L5 - Brookong | Driver behaviour | Avoidable | LH141 reported that project vehicles are not driving to local road conditions and requested that drivers reduce their speed when travelling on Yuluma Road, particularly when pulling onto the road shoulder. | The Land & Access Officer acknowledged the complaint and advised that the Construction team was notified with a reminder issued to the workforce regarding appropriate driving behaviour. |  |  | ACT-132065 | Closed with mitigation | 2025-12-05
2025 | December |  | 2025-12-05 | 12.30pm | Phone call | L5 - Tootool | Gate left open | Avoidable | LH177 reported to the Land & Access Officer that a property gate was left open, and concerned of the effort involved in potentially drafting boxed sheep. | The Land & Access Officer acknowledged the complaint and notified the Construction team to investigate. A meeting held with the landholder to outline measures to prevent recurrence including crews sendiong the Construction Manager photos of closed gates at the end of each shift, and additional pre-start reminders. |  |  | ACT-132168 | Closed with mitigation | 2025-12-15
2025 | December |  | 2025-12-06 | 7.30am | SMS | L5 - Uranqunity | Gate left open | Avoidable | H195 advised the PEC Land & Access Officer that a gate was left open and consequently the landholder's lambs were boxed with ewes. | The Land & Access Officer acknowledged the complaint via phone call and notified the Construction team to investigate. A meeting is to be arranged with landholder to outline measures to prevent recurrence including re-installation of shut the gate sign and image distributed to staff indicating how to secure the gate properly with the supplied lock. |  |  | ACT - 132212 | Closed with mitigation | 2025-12-11
2025 | December |  | 2025-12-11 | 6.45am | Phone call | L5 - Rowan | Gate left open | Avoidable | The Land & Access Officer contacted H205 reporting that a gate had been left open, allowing young rams to leave their paddock and enter an adjoining laneway. The landholder advised that this gate must remain closed at all times. | The Land Access Officer returned the rams to their paddock and secured the gate. PEC waste items also removed rmeoved from property. The Construction team advised that crews will send the Construction Manager images of locked gates at the end of each work shift. A meeting was held with the landholder discussing the additional mitigations. |  |  | ACT-132983 | Closed with mitigation | 2025-12-15
2025 | December |  | 2025-12-13 | 1.35pm | SMS | L2 - Carrathool | Easement registration payment | Unavoidable | PEC L/H083 advised the Land & Access Officer that he has locked his gates and is denying project access to his property pending receipt of payment from Transgrid under the Easement Option program. | The matter has been escalated to Transgrid. Transgrid will provide the landholder with a further update regarding the status of the Special Benefits Scheme payment and any outstanding administrative requirements to be completed. |  |  | ACT-133403 | Closed | 2025-12-15
2025 | December |  | 2025-12-16 | 7.35am | SMS | L5 - Uranqunity | Gate left open | Avoidable | H195 advised the PEC Land & Access Officer that his gate was shut but not locked as agreeed due to an insurance policy /claim. Gate locked with L/H lock. | The matter referred to the Construction Team with additional mitigation of crews sending an image of the locked gate at the end of each work shift to the Construction Manager. The Landholder was satisifed to trial the new process. |  |  | ACT-133465 | Closed with mitigation | 2026-12-19 | press forward
2025 | December |  | 2025-12-16 | 2.25pm | Phone call | L5- Rowan | Vehicles using incorrect access point | Avoidbale | H197 lodged a complaint with the Land Access Officer advising that PEC construction staff exited the property via a cattle grid rather than the approved construction access point, and advised that ongoing non-compliance may result in access being revoked. | The L&A Team acknowledged the complaint and advised the Construction Manager of the issue. PEC Sub-contractor crews were reminded of the approved off-easement access route and procedures. The Landowner was satisfied with the reminder but insisted procedure must be followed. |  |  | ACT-133953 | Closed | 2026-12-18
2025 | December |  | 2025-12-24 | 10.20am | Phone call | L2 | Animal welfare and PEC flagging | Avoidable | LH082 called the Land Access Officer advising he had discovered six cows that had perished from what appears to be plastic ingestion relatiing to PEC flagging and debris. The L/H will be submitting costs to the project in the new year and seeking reimbursement. | The Land Access Officer acknowleged the complaint and agreed with the landowner that a meeting will take place following the project Christmas shutdown to discuss costs for reimbursement. The Landowner has removed the flagging and plastic debris from his property to prevent recurrence. |  |  | ACT-134638 | Closed with a commitment | 2025-12-24
2026 | January |  | 2026-01-15 | 11am | Meeting | L5 | Unsatisfactory Rehab on property | Avoidable | H193 L/H advsied the Land Acess Officer that he is not satisfied with rehabiltation works on his property. He noted that in his agreement the property is to be reinstated to a condition that is the same or better than pre-construction condition. | The Land Access Team & Construction Supervisor met with landholder and viewed the property rehabilitation area. A commitment is now in place for the Rehabiltation Team to remove the rocks and level the site to landholder's satisfaction prior to completion documentation will be signed. |  |  | ACT-135511 | Closed with a commitment | 2026-01-16
2026 | January |  | 2026-01-19 | 5.07pm | Phone call | L5 | Gate left unlocked | Avoidable | H195 advised PEC Land & Access Officer that his gate was shut but not locked as agreed to and outlined in the insurance policy. The gate was locked by the Landholder until an onsite meeting. | The complaint was acknowledged and the matter referred to the Construction Team for investigation and consideration of mitigations. The Land Access team is seeking a follow-up meeting with the Landholder |  |  | ACT-137586 | Closed with a commitment | 2026-01-21
2026 | January |  | 2026-01-20 | 12.30pm | Phone call | L5 - Uranquinty | Gate left open | Avoidable | H196 advised the PEC Land Access Officer that a gate had been left open, resulting in neighbouring sheep entering his property. | The Land Access Officer acknowledged the complaint and met the landholder onsite with a senior construction supervisor to discuss the issue and reinforce with the onsite crews the requirements for gates to be closed at all times. The sheep were mustered back into the correct paddock, and the neighbouring owner was advised. The Landholder was satisfied with the Supervisor's instruction to staff. |  |  | ACT-135902 | Closed with a commitment | 2026-01-20
2026 | January |  | 2026-01-23 | 10.15am | Email | Wagga | Road dust | Avoidable | The Transgrid community team shared three complaints regarding vehicles causing dust while travelling on Redbank Road, which is unsealed. | An investigation confirmed that the complaints related to vehicles from HumeLink West and not EnergyConnect. Transgrid responded to the complainants accordingly. |  |  | ACT-136905 | Closed | 2026-01-23
2026 | January |  | 2026-01-26 | 7.00am | SMS | L5 - Uranquinty | Unauthorised property access | Avoidable | The Land Access Officer received a notification from LH188 advising that a vehicle was observed entering the property without authorised access. | The Land Access Officer acknowledged the complaint and notified the Construction Supervisor. An investigation confirmed the vehicle had mistakenly accessed the landholder’s property while inspecting an incorrect transmission tower. The crew were instructed to immediately leave the property. The Land Access Officer advised the landholder of the outcome, who confirmed they were satisfied with the response. |  |  | ACT-136911 | Closed | 2026-01-26
2026 | January |  | 2026-01-30 | 11.45am | Phone Call | L5- The Rock | Easement registration payment | Avoidable | PEC L/H185 advised the Transgrid Land & Access Manager that he has locked his gates and is denying project access to his property pending receipt of payment from Transgrid under the Easement Option program. | The matter was escalated to Transgrid management. Transgrid arranged a meeting with the landholder to provide an update on the payment status and to address any outstanding issues, with the aim of ensuring construction access remains in place to ensure completion of project works. The landholder was satisified with the update. |  |  | ACT-137967 | Closed with a commitment | 2026-01-30
2026 | February |  | 2026-02-13 | 8:00 | Phone Call | L5- Cullivel | Construction sequenciing | Avoidable | LH134 contacted the PEC Land Access Manager to express frustration about multiple crew visits to the same tower within the easement. | The Land Access Manager acknowledged the concern and advised that the construction program is complex, with multiple specialised crews required to undertake works prior to energisation. An onsite meeting was held with the landholder to outline the program of works, explain the required sequencing, and address concerns. |  |  | ACT-138870 | Closed | 2026-02-16
|  |  | 2025-07-31 | [5 empty] | EA & TG using grid and not designated gates |  |  |  |  | ACT-135511
9.58am
L5 – Tootool
Road condition