## PECe
Project EnergyConnect (Eastern Section) Complaints Register
Year | Month | Number of Complaints | Method of Notification | Nature of Complaint | Description | Action Taken | Status
2023 | March | 1 | Telephone | Traffic Management | Long delays and disurption to local traffic | Complaints investigated. Traffic control looking at ways to reduce delays for local traffic. Some small adjustments have been made to the programming of the traffic lights that do not compromise worker or public safety. Resident contacted by phone to explain traffic management process and offered face to face meeting. | Closed
2023 | April | No complaints registered to date
2023 | May | No complaints registered to date
2023 | June | No complaints registered to date
2023 | July | No complaints registered to date
2023 | August | No complaints registered to date
2023 | September | 3 | Email from Arch Services on behalf of complaintant. | Use of Channel 14 on radio | At first the complaint was regarding bad language being used by contractors on channel 40. After phonecalls by both Transgrid and SecureEnergy it was realised that the complaint was more about the use of Channel 14 - a common channel used by local farmers in Lockhart. The complaintant wanted SecureEnergy to cease using any channels between 1 and 30. | Complaint investigated. SecureEnergy does not use Channel 40 at all. We do however use Channels 14, 15 and 17 in the local area. Discussions with the Construction Team regarding radio etiquette on any channel and this is being reinforced in daily prestarts. Still discussing with the Construction Team about using Channels 30-40 instead. Our Land and Property Access Manager is also contacting some of our landholders in the area to see what channel is not often used by the farmers. Our Construction Delivery Manager has agreed to change Channel 14 to a less used channel. Currently investigating options. TG have been in contact with complaintant to outline actions. SEJV have contacted several landholders to discuss the use of Channel 14, the general reply regarding the UHF use was that providing the radio is used professionally for short discussions there should be no complaints. Investigating radio protocols and site notice will go out to all staff outlining protocols for use of radios. | Closed
| September |  | Telephone from landholder | Gates left open | Landholder is angry that site crews failed to close two gates on his property with one being a property gate. | Complaint investigated using IVMS data from vehicles. The last contractor to access his property was completing geotechnical testing. The data showed both vehicles involved stopped for an extended period at the time at the property boundary and between properties indicating they would be opening and closing gates in that time frame. We are still awaiting two more subcontractor IVMS records to show their movements on the day. We have again reiterated the closing of gates in prestarts. SEJV have provided updates to the landholder. Landholder providing quote of damage to cattle. | Closed
| September |  | Telephone from landholder | A subcontractor driving a low loader along Hanging Rock Road speeding whilst negotiating a bend. | Landholder very concerned and considered this a near miss. The landholder was very upset by this near miss as a similiar incident occurred in the past killing someone close to her. | The landholder has been contacted numerous times to update her on our actions. The incident has been raised with the SecureEnergy Project Manager who has reported the incident to the subcontractors management. Currently we are awaiting feedback from him on the actions they will put in place to address the complaint and what they will do to ensure their staff attend to the speed restrictions along this road. Investigating reducing the speed limit on Boiling Down Road for all project vehicle movements. Driver in question has been reprimaded for the incident. | Closed
2023 | October | No complaints registered
2023 | November | 2 | Verbal advice to onsite crews. Email from landholder (lessee) lawyers on H 195 to Transgrid on 24 November 2023. | Project equipment required to enter property not presented in a manner of satisfactory cleanness for the approval by the landholder to enter the property. Machinery was inspected off the project alignment and had not entered the property. The inspection process was part of the Property Management Plan and Biosecurity Plan conditions. | Landholder concerned the vegetable matter and soil on the equipment could fall from the machine whilst travelling through the property and may introduce unwanted species of weeds & grasses onto the property. | Equipment did not enter the property and was returned to the Elecnor Australia yard for additional cleaning. No attempt to access the property after additional cleaning of the equipment was made. For noting actions include: • Internal meetings to review landholder Property Management Plan. • New Induction created for access onto property for all Construction and Subcontractors. | Closed
2023 | November |  | Email from local resident. | Environmental complaint relating to clearing of large trees at Brookong State Forest. | The complainant has criticised the loss of big trees that have been felled in the Brookong Forest near Lockhart and wants to know why this forest has been chosen as a as a location for the infrastructure project. The complainant also states they have experienced emotional distress as a result of our actions and is want to know what compensation if any, is available. | Transgrid has responded to the Complainant by explaining the selection process for the EnergyConnect corridor. The vegetation clearing at Brookong State Forest is also in line with all relevant environmental approvals for the project as well as the mitigation measures in place to minimise impact to fauna in the area. Finally, to the second part of the complaint, Transgrid does not offer personal compensation n for emotional distress associated with clearing within Brookong State Forest. | Closed
2023 | December | 2 | Letter from a landholder's solicitor. | Landholder complaint relating to biosecurity protocols not being followed as part of an ongoing complaint, first raised in September 2023. | The complainant found an excavator covered in foreign plant matter and soil found on his property, raising concerns about biosecurity. | The project team are investigating current procedures and identifying where improvements can be made with regards to ensuring appropriate processes are followed. Internal investigations indicated greater care to be taken when cleaning plant and equipment. Additional training for Project operators regarding plant clean down procedures have been performed at the Lockhart wash down facility. | Closed
2023 | December |  | Verbal advice | Landholder conveyed dissatisfaction over the arrival of a construction grader on his property without prior notification. This occurred during harvest. | The landholder's harvesting operation was impeded by construction activities, resulting the landholder standing down. | Investigations into the incident and discussions with the landholder to resolve the issue hvae occurred. The investigation indicated the possible factors that contributed to the incident were: Inadequate communications Expediting daily productions insufficient scrutiny by Land Access Team and lack of briefing during hand over of supervision roles. These matters have been attended internally through personal discussions between Supervisors and Managers, pre start meetings and review of Project section inductions. | Closed