## PECw
Project EnergyConnect (Western Section) Complaints Register
Year | Month | Date | Time Received | Number of Complaints | How complaint was received | LGA | Topics Raised | Avoidable / Unavoidable | Summary | Responses and Investigation | Salesforce ID | Oustanding Actions | Status | Date Closed
2022 | NA |  |  | No complaints registered to date
2023 | January-April |  |  | No complaints registered to date
2023 | April |  |  | No complaints registered to date
2023 | May |  |  | No complaints registered to date
2023 | June |  |  | No complaints registered to date
2023 | July |  |  | No complaints registered to date
2023 | August |  |  | No complaints registered to date
2023 | September |  |  | No complaints registered to date
2023 | October |  |  | No complaints registered
2023 | November |  |  | No complaints registered
2023 | December |  |  | No complaints registered
2024 | January |  |  | No complaints registered
2024 | February |  |  | 1 | Verbal |  | Speeding on road whilst livestock crossing. |  | Property Owner on Arumpo Road in Buronga not satisfied with speed of a subcontractor on the road whilst he was walking his livestock across it. He thought the driver was speeding. | Management advised of the incident. Investigating incident and signage on road. Elecnor Australia has spoken to the property owner (current landholder). Landholder failed to advise Elecnor Australia of movement of sheep as has been arranged previously due to the unplanned nature and late afternoon timing of stock movement. Stock warning signs not clearly visible on side of road. Driver has apologised to the landholder. Elecnor Australia is assisting the landholder in making stock warning signs more visible to the public. |  |  | Closed
2024 | February |  |  | 1 | Verbal |  | SecureEnergy vehicles seen speeding in Wentworth on their way to the Old Renmark Road (via the Silver City Highway) at 5.30am. |  | Police contacted EA to advise that a member of the public had seen SecureEnergy vehicles travelling at 100km per hour in a 60km zone in the township of Wentworth. Police have advised this is the second time this caller has contacted them. This is the first-time police have contacted EA. | EA has contacted the resident. EA workers have been advised at today's pre-start (Tuesday, 20 February 2024) that speeding drivers will be targeted by the Highway Patrol. A review is also underway of any IVMS alerts from the Wentworth area. |  |  | Closed
2024 | March |  |  | No complaints registered
2024 | April |  |  | No complaints registered
2024 | May |  |  | No complaints registered
2024 | June |  |  | No complaints registered
2024 | July |  |  | No complaints registered
2024 | Aug |  |  | No complaints registered
2024 | Sept |  |  | No complaints registered
2024 | Oct |  |  | No complaints registered
2024 | Nov |  |  | No complaints registered
2024 | Dec |  |  | No complaints registered
2025 | Jan |  |  | No complaints registered
2025 | Feb |  |  | No complaints registered
2025 | Mar |  |  | No complaints registered
2025 | April |  |  | No complaints registered
2025 | May |  |  | No complaints registered
2025 | June |  |  | No complaints registered
2025 | July |  |  | No complaints registered
2025 | August |  |  | No complaints registered
2025 | September |  |  | No complaints registered
2025 | October |  |  | No complaints registered
2025 | November |  |  | No complaints registered
2025 | December |  |  | No complaints registered
2026 | January |  |  | No complaints registered
2026 | February |  |  | No complaints registered
2026 | March |  |  | No complaints registered