## HumeLink East
Humelink East Project Complaints Register
Year | Month | Date | Time Received | Number of Complaints | How complaint was received | LGA | Topics Raised | Avoidable / Unavoidable | Summary | Responses and Investigation |  | Outstanding Actions | Status | Date Closed
2024 | November | 27/11/2024 | 12pm | 1 | Email | Yass Valley | Minor complaint - re: interactions with stakeholder | Avoidable | Received a complaint from from stakeholder about some interactions leading up to an event involving cultural activities and before the event. | Email sent with contact details to stakeholder Investigation was undertaken Phone call made to stakeholder Further discussions 13/12/2024 - Phone call and further emails Undertake lessons learnt Email out - 17 December 2024 recorded complaint | Activity number - ACT-88390 - ACT -89127 | None | Closed | 2024-09-12
2024 | December | 2024-06-12 | AM | 1 | Text Message | Yass Valley | Participation on the project | Unavoidable | Stakeholder sent a text to complain about how they felt they werent included in the procurement process for the project. Advised they do not live on country anymore but felt they should still be able to be a representative working on the project. | Response: Phone call 6/12 at 3pm. emailed stakeholder - advised they could participate on the project will record complaint response sent - 9/12/2024 - expression of interest form was sent to stakeholder | Activity number ACT-89130 | None | Closed | 2024-09-12
2025 | January | 2025-01-31 | AM | 1 | Phone call | Yass Valley | Property Management Plan meeting | Avoidable | Landowner called Transgrid complaining that the HumeLink East contractor rejected the request by the landowner for the Transgrid Landowner Access Officer to attend a meeting with the contractor and landowner to discuss the Property Management Plan. | ~ Landowner called Transgrid Landowner Access Officer on 31/1/2025 at 9:30am ~ Complaint recorded Contact landowner to confirm that Transgrid Landowner Access Officer will attend PMP meeting with contractor. | Activity number: ACT-92451 | None | Closed
2025 | February | 2025-02-06 | 11:24am | 1 | Phone call | Cootamundra/Gundagai | Road being damaged by trucks entering compound | Unavoidable | HumeLink East Place Manager (and Interface Manager in a separate call) received a call from a Cootamundra-Gundagai Regional council member about concerns raised by a local resident to the Council regarding road damage from trucks entering and leaving the new site compound in Adjungbilly. | HumeLink East Place Manager advised the council member that the HumeLink East team would investigate. Note that a pre-condition survey of this location has been completed prior to works. The project team inspected the site and confirmed no change in condition of the road, compared to the pre-condition survey. Documented in photographs. The project team has provided an update to the council member who shared the complaint. Project team to follow up with Council to check whether the resident would like a call to discuss. The project team will continue to monitor the condition of the road as there will be further heavy vehicle movements. An ongoing maintenance regime will be implemented ensuring any critical safety issues are addressed in a timely manner. Upon completion of the works in the area, a post-construction condition survey will be undertaken and any remedial works identified in consultation with the council will be completed. | Activity Number - ACT - 95585 | None | Closed | 2025-02-06
2025 | February | 2025-02-12 | 9.17am | 1 | Email | Yass Valley | Poor driving behaviour of a HumeLink East member of staff driving a Company vehicle. | Avoidable | The community member advised by email that they were tailgated by a HumeLink East branded vehicle in a school zone in Yass at the end of drop-off time on this day. The driver then turned in front of a learner driver at traffic lights where the learner had right of way. | A HumeLink East Place Manager has contacted the community member by phone. Confirmed that poor driving behaviour is not tolerated, and HumeLink East would raise this in the pre-starts and toolbox talks to occur prior to work this week. The General Superintendent for HumeLink East was also called and the incident reported to him so this can be raised in pre-starts and toolboxes and code of driving conducted reiterated. The community member was unsure of the vehicle's number. The community member was satisfied by the project's swift response and actions of the project. Incident raised in pre-starts and toolboxes and code of driving conducted reiterated. HumeLink East sought to identify the driver and vehicle through HumeLink East vehicle tracking software. However, the vehicle could not be identified as the time of event could not be determined excatly. | Activity Number ACT-94176 | None | Closed | 2025-02-12
2025 | March | 2025-03-24 | 1.06pm | 1 | Email | Upper Lachlan Shire | Gates left half open and latches not clipped | Avoidable | The Landowner emailed to advise the gates had been left half open and latches were not clipped on properly. There was a high risk of livestock getting out. | The Humelink Place Manager has contacted the Landowner by phone and discussed the issues raised. Advised the teams will be reminded again in pre-starts and tool box talks prior to work each day. This has been raised to senior management. The landowner was understanding and advised that it is very important that gates are left as found and any latches should be checked to make sure they are closed correctly. | Activity number ACT- 97316 | None | Closed | 24/3/2025
2025 | March | 2025-03-11 | 10am | 1 | Email | Upper Lachlan Shire | HumeLink East supervisor and contractor drove onto a landowner's property, unauthorised and unannounced, and had not adhered to agreed biosecurity practices. | Avoidable | Complaint came through Transgrid from the Australian Energy Infrastructure Commissioner on 27 March 2025. The landowner has requested an apology. The HumeLink East supervisor and contractor went onto the wrong property as they were given an incorrect address. Upon learning of the error, the supervisor apologised to the landowner. | This occurrence resulted from an inadvertent error involving an incorrect address supplied to the HumeLink East supervisor. When informed of the error by the landowner, the supervisor immediately apologised. HumeLink East has taken this matter seriously, conducted a thorough review of their processes, and implemented the necessary changes to avoid a similar incident in the future. Transgrid has written to the landowner, apologising for this incident. | Activity number - ACT 97761 | None | Closed | 2025-04-01
2025 | March | 2025-03-25 | 10.24am | 1 | Email | Yass Valley | Transgrid transmission easement and access track property acquisition process | Unavoidable | The landowners have contacted EWON. Their claims about Transgrid include: providing misleading information, lack of engagement, delay tactics, incomplete ecology survey on the property, refusal to alter the alignment across a neighbouring property. The landowners say they have suggested an alternative alignment option which would avoid sensitive locations on their property, | Transgrid has been engaging with the landowners since 2020 and most recently had been investigating alternative transmission line alignment and access track locations on the landowners' property. Transgrid has been instructed not to contact the landowners further at this stage and to provide information for a resolution. Response to EWON sent on 04/04/2025. EWON requested further information. Response sent to EWON on15/04/2025. | Activity number - ACT 98433 | None | Closed | 2025-05-02
2025 | April | 2025-04-04 | 12.22pm | 1 | Phone call | Sydney | Availability of RAP work on the project; concern around the allocation of work for the project; concern that they had not been selected to work on the project | Unavoidable | The complainant runs a business which responded to a tender to provide RAP services but has to date not been selected to do this work. HumeLink East has had an initial meeting with the sub-contractor that is engaged to coordinate those RAP businesses on the project. HumeLink East has returned the call of the complainant to advise it is investigating their concerns. The complainant was unhappy with this call. | HumeLink East is seeking further advice from the RAP sub-contractor regarding the tender response from this business. HumeLink East will review all infomation when provided so as to understand a better way to provide further transparency around RAP allocation processes. HumeLink East has committed to the complainant to contact them again on 07/04/2025 with an update on the investigation. HumeLink East has responded via email (07/04/2025) to this business addressing their concerns around work allocation and the process involved. The matter has been discussed with the RAP sub-contractor. HumeLink East included the project's complaints process in the response. | Activity number - ACT-98910 | None | Closed | 2025-04-07
2025 | May | 2025-05-23 | 4.25pm | 1 | Letter | Snowy Valleys | Poor consultation and engagement with the Bryants. Request for reimbursement for legal costs. | Unavoidable | The complainant has been disappointed with the lack of engagement from the Project on any level of detail or impact to them. They have been away for extended periods of time over the last 18 months and are not aware of the impact of the project on them. Specifically, they highlighted: The only correspondence they have received has been legal in nature; the transmission lines visually impact their property and this will affect the value of their property; they wish to be reimbursed for legal costs that they have incurred; and the project has caused them concern and worry. | 2/6/25 - Transgrid has offered to reimburse legal costs and requested further information from the complainant. The complainant did not respond. 17/6/25 - Transgrid has emailed complainant again with offer to reimburse legal costs. 30/06/25 - No response received from complainant. 1/7/2025 - Complainant ackowledged receipt of emails and said they would provide requested information next week. 6/7/2025 - Complainant provided bank details for reimbursement to occur. 8/7/2025 - Transgrid spoke with the complainant to confirm payment details for reimbursement of legal fees. Payment was transferred on 11/7/2025. | Activity number - ACT-103915 | None | Closed | 2025-07-11
2025 | June | 2025-06-16 | 2.59pm | 1 | Email | Yass Valley | Visual impact, economic impact, poor community consultation. | Unavoidable | The complainant lives next door to a property which will have transmission towers on it. He is concerned about the visual impact he will experience. He also has a glamping business on his prioperty and is concerned about possible affect to this business. He has also raised concerns about not being personally contacted about the HumeLink project and informed of the alignment. | 16/06/25 - The project has called and emailed the complainant regarding his concerns and stated that the matter is being taken seriously. 20/06/25 - Full response to the complainant's questions and request for EIS information was sent to the complainant. A commitment to meet with the complainant was also made. 26/06/25 - Complainant agreed upon a date and time to meet - 3 July. 3/7/2025 - Transgrid met with complainant on their property and explained location of transmission towers and the level of visual impact. Also explained the community engagement that took place over the past three years. 8/7/2025: Follow up email was sent to the complainant confirming the discussion that took place on 3/7/2025. | Activity number - ACT-106621 | None | Closed | 2025-07-08
2025 | July | 2025-07-10 | 12.36pm | 1 | Phone and Email | Cootamundra-Gundagai | HumeLink East representatives accessed the wrong property, without approval | Avoidable | The complainant's legal representative stated that there was unauthorised access to the complainant's property on 7 July 2025. The personnel had entered the property by vehicle and were asked to leave by a representative of the complainant. The personnel responded that they thought they were on a public road and had a right to be there. The complainant's representative then confirmed that the access tracks being driven on were private property, and no arrangements had been made to approve this access. The complainant is requesting further details to be provided upon investigation. | 10/7/2025 - The HumeLink East delivery partner conducted an investigation into its GPS vehicle tracking system and found that no project vehicle traveled on that particular road on that day. 11/7/2025 - Transgrid investigated the movements of its vehicles and, checking GPS data, found that no project vehicles were in the area at the time noted by the complainant. Transgrid advised the complainant's legal representative and requested if more information about the vehicle could be provided, e.g. registration, make or colour. The legal representative said they would follow up with the complainant. 14/7/2025 - The legal representative has provided the registration number and other identifying features of the vehicle, which show it was a HumeLink East vehicle. The delivery partner is investigating. 17/07/2025 -The HumeLink East delivery partner has conducted a thorough investigation into its processes in response to new information. They have identified a gap in the onboarding process and are currently addressing it. Within the next month, the HumeLink East delivery partner will implement a revised education and training program focused on Land Access Protocols and Community Engagement across the entire project. 18/07/2025 - Transgrid wrote to the complainant apologising on behalf of the HumeLink East delivery partner and advised that their delivery partner confirms that the vehicle in question was part of the project team. Transgrid advised that the delivery partner has identified a gap in some of its processes and is actively working to remedy it and will undertake a project wide revised education and awareness training on Landowner and Community Engagement protocols. | Activity number - ACT-110954 | None | Closed | 18/07/2025
2025 | July | 2025-07-10 | 1.48pm | 1 | Email | Snowy Valleys | Landowner concerned about Transgrid processes when communicating reports from sub-contractors. | Avoidable | During a visit to the complainant's property on 30 June, a heritage consultant mentioned that on a previous visit in September 2024, they had taken some artifacts for analysis. The complainant had not been informed of this by Transgrid. The complainant is not concerned that the artefacts were taken, but concerned that Transgrid had not informed them. | 24/07/2025 - Transgrid offerred an apology and said it would improve its communications procedures with landowners around the checking of heritage samples. | Activity number - ACT-111132 | None | Closed | 2025-07-24
2025 | July | 14/07/2025 | 5.00pm | 1 | Phone call | Yass Valley | Truck movements and possible road damage near a bridge | Unavoidable | A Yass Valley Council employee telephoned HumeLink East to report a complaint from a community member regarding truck movements and potential road damage near a bridge on Childowla Road near Bookham. The complaint was received on Friday, July 11; however, the Council employee was on leave and only learned about it on 14 July and therefore only provided it to HumeLink East on 14 July. | 14/07/2025 - The HumeLink East delivery partner is conducting an investigation - review of the road dilapidation report and seeking additional information from Council as to the exact location of the road damage. 17/07/2025 - The HumeLink East delivery partner acknowledged to Council that their project trucks may have contributed/exacerbated the existing road condition and is working through a road maintenance agreement with the Yass Valley Council. The road will be repaired. | Activity number - ACT-111936 | None | Closed | 17/07/2025
2025 | July | 24/07/2025 | 9.20pm | 1 | Phone call | Snowy Valleys | Truck movements and driver behaviour | Unavoidable | A community member telephoned HumeLink East to report driver behaviour at the intersection of Redhill Road and Nanangroe Rd/Adjunbilly Rd. The truck took the corner quickly forcing the driver to pull onto the side of the road urgently. The trailer of the truck had swung into the oncoming lane. | The HumeLink East delivery partner called the community member to confirm details of the incident. The community member could not provide any information about the vehicle except that it was white with silver or black stripes. HumeLink East delivery partner advised the community member that they would run additional project wide workshops/toolbox talks on the project around driver behaviours and sharing the road as the vehicle could not fully be identified as a project vehicle. | Activity number - ACT-112642 | None | Closed | 24/07/2025
2025 | August | 2025-11-08 | 9.17 am | 1 | Email | Cootamundra / Gundagai | Truck movements and possible road damage | Unavoidable | The HumeLink East delivery partner received an email from the Cootamundra Gundagai Regional Council about a complaint from an unknown community member about Parsons Creek Road regarding poor road conditions due to truck movements from the HumeLink East project. The resident submitted video footage, which is being investigated along with Road Condition reports. The HumeLink East delivery partner is consulting with the Council. | 11/08/2025 - HumeLink East delivery partner is undertaking a review with Council and has a meeting set for 12/08/2025 12/08/2025 - HumeLink East delivery partner met with Council which was a positive meeting. Council advised they will respond and close out the complaint via their process. The HumeLink East delivery partner will work with council to undertake minor works and will monitor the road. Open communication channels will be maintained with Council on local roads. | Activity number - ACT-115076 | None | Closed | 2025-12-08
2025 | August | 19/08/2025 | 9.07 am | 1 | Email | Yass Valley | Landowner concerned that a committment to a water crossing upgrade was not going to be delivered by the HumeLink East delivery partner as there was no written confirmation. | Avoidable | The HumeLink East delivery partner received an email from Transgrid advising they had received a complaint from a Landowner regarding the Landowner wanting written confirmation around a water crossing upgrade. | 19/08/25 - The HumeLink East delivery partner phoned the Landowner to discuss concerns and committed to putting the verbal confirmation in writing that the water crossing was going to be upgraded. The HumeLink East delivery partner confimed via email that the water crossing was going to be upgraded. The HumeLink East delivery partner is looking to book (after many attempts over a few weeks) a meeting to discuss in detail the water crossing. | Activity number - ACT-116195 | 11.09.25 - The HumeLinkEast delivery partner met with Landowner and reviewed design and Landowner approved of the works to be undertaken. 02.09.25- Landowner has agreed to a face-to-face meeting on 11 September. Waiting on Landowner to provide a date and time so the HumeLink East delivery partner can discuss the water crossing in detail. Landowner provided advice that they were shearing at present and were not available to meet until this was completed. Week commencing 1 Sept HumeLink East will reach out. | Closed | 2025-09-11
2025 | August | 22/08/25 | 1.56 pm | 1 | Email | Yass Valley | Lessee has raised a complaint about material being taken off-site without approval/discussion at the Faulder Avenue Conductor Storage Site. | Avoidable | Transgrid received the complaint from the stakeholder and provided advice to the HumeLink East delivery partner via phone call in the first instance followed by an email. The HumeLink East delivery partner is investigating has spoken with the lessee and is arranging a face to face meeting when landowner is available next week. | The HumeLink East delivery partner called the landowner and landowner has agreed to meet next week. The HumeLink East delivery partner will call the landowner 24hours before to ensure that the landowner is available. Transgrid is now managing this complaint, as it is located within their lease holding. | Activity number - ACT-116958 and ACT-116785 | HumeLink East to call Landowner - Monday 25/08 Transgrid will now manage this complaint as the lessor of the property. | Closed | 25/08/2025
2025 | August | 22/08/25 | 9.58 am | 1 | Email | Yass Valley | Truck movements - possible speeding | Avoidable | Transgrid received the complaint via the community inbox and forwarded to the HumeLink East delivery partner. The contact information for the stakeholder was only via email. The stakeholder did not provide any vehichle detail regarding particular vehicles using Fairyhole Road, Yass. The HumeLink East delivery partner - emailed the stakeholder seeking additional information. | The HumeLink East delivery partner, can confirm that Fairyhole Road is being utilised by the project and had emailed the stakeholder for more information. | Activity number - ACT-116985 | Email sent to stakeholder (as only contact information). No response provided back to email. | Closed | 22/08/2025
2025 | September | 2025-10-09 | 11.17am | 1 | Email | Yass Valley | Truck movements, road condition | Unavoidable | Transgrid received the complaint via the community inbox and forwarded to the HumeLink East delivery partner. The contact information for the stakeholder was only via email. The stakeholder advised that they had put in a complaint on-line on the 05/09/25 - however neither Transgrid or their delivery partner have been able to source the complaint. The complaint was focused on the deterioration of Fairyhole Road and truck usage. | The HumeLink delivery partner emailed the stakeholder to confirm that they are in discussions with the Yass Valley Council around repair. | Activity number - ACT-120969 | 10/09/25 - Email sent to stakeholder to advise the HumeLink East Delivery partner is meeting with the Yass Valley Council 11/09/25 | Closed | 2025-11-09
2025 | September | 23/09/2025 | 3.11 pm | 1 | Phone call | Upper Lachlan Shire | Dust concerns and lack of timely notification | Avoidable | Stakeholder placed a call to Transgrid's call centre, who notified the HumeLink East delivery partner. The HumeLink East delivery partner contacted the stakeholder who's primary concern was that they had previously contacted the HumeLink East delivery partner regarding dust concerns and was advised at the time that the HumeLink East delivery partner would get back to them with more information around dust management. This did not occur and the stakeholder placed the call today. | The HumeLink East delivery partner phoned the stakeholderat 3.36pm and apologised for the delay in returning information. The stakeholder was able to clarify their concerns with the delivery partner. Specifically, that two previous projects - not related to HumeLink - did not manage dust along the road and the stakeholder was not willing to put up with this again with another project. HumeLink East arranged to meet with the stakeholder at 4pm on Wednesday 1 October 2025 at their property to better understand the stakeholder's concerns with future project traffic and their request to have the dirt road sealed. | Activity number - ACT-122554 | 23/09/2025 - Phone call to stakeholder and meeting arranged @4pm 01.10.25 01/10/2025 - meeting held - apology for the delay in response time accepted by the stakeholder. The HumeLink East team are working with Councils on Road Maintenance. | Closed | 2025-01-10
2025 | September | 30/09/2025 (complaint sent) 8/10/2025 (complaint received) | 12pm | 1 | Transgrid Website Enquiry Form | Goulburn Mulwaree | HumeLink vehicles taking up all-day public parking spots in Goulburn | Avoidable | Note: Due to a Transgrid website problem, this complaint did not come through until 8/10/2025. The commu nity member raised concern about the number of identifiable project vehicles using more than 25 all-day parking spots around a public library and gallery (Church St, Goulburn). The HumeLink project office is located across the road from the public buildings. Taking up these parking spots impacts community members and workers who need to access the public buildings. | HumeLink project personnel with the delivery partner and with Transgrid have again been directed to not park in Church St, and to instead utilise a car park in Ellesmore St. This direction on parking will be re-issued every month, to remind staff and ensure any new personnel are also aware. | Activity Number - ACT-122308 | None | Closed | 2025-10-13
2025 | October | 21/10/2025 | 3.43 pm | 1 | Email | Goulburn Mulwaree | HumeLink vehicles parking along Bourke Street | Unavoidable | A email was sent 21.10.25 to the HumeLink East delivery parter to private email. It was not opened until 22.10.25 as the indvidual was away. Actioned 22.10.25 and responded to council immediately. The HumeLink East delivery partner then telephoned the Council and made an appointment @2pm. | The HumeLink East delivery partner met with Council and provided advice to Council that they had already been asking their staff to park in other locations. Council was positive in their response to this information. The Council and the HumeLink Delivery partner agreed that the project was within its rights to park their vehicles where they were. It was acknowledged that there was a perception that the vehicles were overstaying in locations because they all looked the same. The HumeLink East Delivery partner will reach out to stakeholders in conjunction with the Council to review parking locations. The Council were satisfied with this. | Activity Numbers - ACT-125437 ACT-125449 ACT-126083 | 22.10.25 - Council to provide the HumeLink East Delivery partner names of businesses. Council sent email 29.10.2025 advising they would be taking no further action. | Closed | 29/10/2025
2025 | November | 3/11/2025. | 9.41 pm | 1 | Email | Yass Valley | Truck movements, road condition, driver behaviour | Unavoidable | Transgrid received the complaint via the community inbox and forwarded it to the HumeLink East delivery partner. The stakeholder's contact information was only via email. The stakeholder did not provide any vehicle details regarding particular vehicles using Flacknell Creek Road. The HumeLink East delivery partner emailed the stakeholder seeking additional information. | The HumeLink East delivery partner, can confirm that Flacknell Creek Road is being utilised by the project and had emailed the stakeholder for more information. The HumeLink East delivery partner emailed the stakeholder and provided the following fact sheets:- Works duration; SMS Alert; Heavy Vehicle routes; and Road use. Stakeholder provided information that some of the roads in the Heavey Vehicle Routes were in the wrong councils. | Activity Number - ACT-126931 | Email sent to stakeholder (as only contact information). Stakeholder responded to email. Advised | Closed | 2025-04-11
2025 | December | 2/12/2025. | 4.46 pm | 1 | Phone call | Upper Lachlan Shire | Truck movements, driver behaviour | Unavoidable | Stakeholder advised that an unbranded truck and trailer which was heading east towards Gunning was in the oncoming lane while the driver was heading in the other direction into Gunning. The driver pulled to the side of the road and nearly hit the guard rail. The caller believed the truck to be speeding. | The HumeLink East delivery partner phoned the caller, who was grateful for the call and advised that they did not require a follow-up. The HumeLink East delivery partner will provide an email to the stakeholder providing additional information around project road use and signing up to the SMS alert program for vehicle movements and notifications. | ACT-131918 | Phone call made to the stakeholder 03/12/2025 | Closed | 2025-03-12
2025 | December | 3/12/2025. | 8.43 am | 1 | Phone call | Upper Lachlan Shire | Truck movements, driver behaviour | Unavoidable | Stakeholder advised that ALL trucks that drive through Dalton are speeding and not staying in their lanes. This is causing concern for the stakeholder as they had to swerve to miss the truck. The incident occurred on Rye Park Rd heading out of Dalton. | The HumeLink East delivery partner called the stakeholder. They were able to provide additional information regarding the vehicle which HumeLink East is now investigating. The HumeLink East delivery partner will provide an email to the stakeholder providing additional information around project road use and signing up to the SMS alert program for vehicle movements and notifications. | ACT-131893 | Phone call made to stakeholder 03/12/2025 | Closed | 2025-03-04
2025 | December | 03/12/2025. | 11.50 am | 1 | Phone call | Upper Lachlan Shire | Truck movements, driver behaviour | Avoidable | Stakeholder advised that truck drivers are behaving badly through the town of Dalton. The stakeholder advised that there is use of exhaust breaking from 6am and that trucks are not staying on their side of the road when using corners. Stakeholder advised that people are being driven off the road. | The HumeLink East delivery partner phoned the stakeholder advising that we take these incidents seriously and would provide this feedback to the project delivery team and have a reminder around driver behaviour sent to trucking companies to remind their employees around driver behaviours. The HumeLink East delivery partner will provide an email to the stakeholder providing additional information around project road use and signing up to the SMS alert program for vehicle movements and notifications | ACT-131929 | Phone call made to stakeholder 03/12/2025 | Closed | 3/12/2025.
2025 | December | 09/12/2025. | 2.49 pm | 1 | Phone call | Upper Lachlan Shire | Dust - caused by vehicle movements on un-sealed road. | Unavoidable | A stakeholder called to express concern that there are not enough water trucks being used in front of her home on Prices Lane. She expected the speed limit to be reduced and requested prior notice about project vehicle movements. | The HumeLink East delivery partner called the stakeholder to confirm they were investigating both short-term and long-term dust suppression measures. | ACT-134701 | Phone call made to stakeholder 09/12/2025 Email sent to stakeholder confirming conversation 10/12/2025 Refer below - this became ongoing and is closed out in final complaint. | Closed | 19/12/2025.
2025 | December | 10/12.2025. | 3.41 pm | 1 | Phone call | Upper Lachlan Shire | Heavy Vehicle speeding | Avoidable | Stakeholder advised that they witnessed a truck with the registration number YNG 4DK. They advised they followed the vehicle to get the registration number as the stakeholders believed it to be speeding. They estimate that the speed was 120km/hr in a 100km/hr zone. The vehicle was heading towards Dalton on the Gunning Road. | The HumeLink East delivery partner has reviewed it GPS tracking of vehicles with no vehicles implicated. The HumeLink East delivery partner has provided the registration number to it sub-contractors and is awaiting their advice if the vehicle belongs to one of their drivers. Stakeholder was directed to HumeLink West in the first instance. The HumeLink East delivery partner received the information 10/12/2025 at 3.30pm. The HumeLink East delivery partner returned call at 4.09 pm. | ACT - 132942 | Phone call made to stakeholder 10/12/2025. | Closed | 10/12/2025.
2025 | December | 10/12/2025. | 4.20pm | 1 | Phone call | Upper Lachlan Shire | Dangerous driving and visibility on road | Avoidable | Stakeholder called to advise of a near miss. They advised they were heading towards Dalton on Rye Park Road between Offleys Lane and Greendale Road, Broadway when a Divalls truck came out of the project site without stopping. To the stakeholder, it appeared that the driver did not stop to check for vehicles. Stakeholder advised they had to break hard so as not to collide with the truck. Stakeholder also advised that the dust on the dirt road reduces vision of oncoming traffic. Stakeholder suggested solution for a stop sign to be put at the entrance. Stakeholder advised they have had other driving issues with this site. | The HumeLink East delivery partner is investigating this with its subcontractor Divalls. The HumeLink East delivery partner has phoned the stakeholder and discussed the events. The stakeholder would like confirmation that Divalls has been spoken with. The HumeLink East delivery partner will provide an email to the stakeholder providing additional information around project road use and signing up to the SMS alert program for vehicle movements and notifications | ACT-133220 | Phone call made to stakeholder 10/12/2025. | Closed | 12/12/2025.
2025 | December | 11/12/2025. | 8.20am | 1 | Email | Upper Lachlan Shire | Dust | Unavoidable | Stakeholder called to advise that the water truck ran eight minutes after two double-trailer trucks had driven past at 6.12am. | The stakeholder has previously advised (in Sept) specifically, that two previous projects - not related to HumeLink - did not manage dust along the road and the stakeholder was not willing to put up with this again with another project and they wanted the dirt road to be upgtraded to a sealed road. Rather than relying on water trucks, the HumeLink East delivery partner has advised that it is investigating a longer lasting solution to minimise dust involving a polymer treatment. It is testing this polymer on a small section of road in another location and is waiting on the trial results. In the interim, the project is investigating the potential for dust monitoring at the property. The stakeholder has progessed to commentary based information rather than complaint. The HumeLink East delivery partners is looking at placing polymer on the roads as a dust management tool. | ACT-134702 | Email to stakeholder Refer below - this became ongoing and is closed out in final complaint. | Closed | 19/12/2025.
2025 | December | 12/12/2025. | 8.49am | 1 | Phone call | Upper Lachlan Shire | Dust driver behaviour | Unavoidable | Stakeholder call ed to advise of bad driver behaviour over the last few days. Stakeholder advised that there are very narrow portions of road where there is nowhere for vehicles to move to the side to avoid oncoming vehicles. Stakeholder commented that school buses would be affected. Stakeholder raised concerns around speed of trucks a lack of visibility and about dust. In particular, along Prices Lane and Gurrundah Road advising that it was severe. Stakeholder did advise that water trucks have been seen multiple times a day. Stakeholder raised concerns around dust affecting water tanks at residents homes. | The HumeLink East delivery partner is investigating a longer lasting solution to minimise dust involving a polymer treatment, rather than relying on water trucks. Stakeholder advised, that they wanted the project to be aware of truck speeds and the narrow road. The HumeLink East delivery partner is discussing driver behaviours with its trucking companies and quarry suppliers. | ACT-133177 | Phone call made to stakeholder 12/12/2025. - voice mail message left. Phone call made to stakeholder 15/12/25. following returned call. | Closed | 15/12/2025.
2025 | December | 12/12/2025. | 12.04pm | 1 | Phone call | Upper Lachlan Shire | Dust | Unavoidable | AGJV call - stakeholder advised that the road needed to be watered. That the trucks were travelling too fast and creating dust. The stakeholder advised they had never seen a water truck along the road. The stakeholder advised that their house gutters are full of dust, and they were concerned that when it rains that the water tank will get filled with mud. The stakeholder advised they cannot open their windows due the amount of dust or hang out the washing. Stakeholder advised that there were asthmatics in the house. | The HumeLink East delivery partner is investigating a longer lasting solution to minimise dust involving a polymer treatment, rather than relying on water trucks and advised that the construction process occurs in phases on this project, unlike other projects. Fact sheets were provided and SMS program explained, which the stakeholder was interested in signing up to. | ACT-133195, ACT-134702, ACT-134701 | Phone call made to stakeholder 12/12/2025; 19/12/2025 to advise of steel deliveries, water truck usage and placement of polymer. | Closed | 12/12/2025.
2025 | December | 12/12/2025. | 4.43pm | 1 | Email | Yass Valley | Alledged tresspass | TBC | Transgrid received notification, via the landowner's lawyer, of an alleged tresspass by a HumeLink East vehicle onto a landowner property. | The HumeLink East delivery partner is investigating this. Transgrid has requested for additional information to identify the vehicle, through the landowner's lawyer. 14/1 - Following repeated requests of landowner's lawyer for further information that would assist with investigating the alleged trespass, no further information has been forthcoming. This complaint has been closed | ACT-133271 | Investigation on vehicle movements | Closed | 2026-01-14
2025 | December | 17/12/2025. | 4.56pm | 1 | Email | Upper Lachlan Shire | Dust | Unavoidable | Stakeholder emailed the HumeLink East delivery partner advised that the dust from the road caused by truck movements. The stakeholder advised that the dust is having an impact on their business, animals and human health. | The HumeLink East delivery partner is investigating a longer lasting solution to minimise dust involving a polymer treatment, rather than relying on water trucks and advised that the construction process occurs in phases on this project, unlike other projects. They will be applying a polymer at the front of the property tomorrow. The stakeholder was happy with that outcome. | ACT-133882 | Phone call made to stakeholder 17/12/2025. | Closed | 17/12/2025.
2025 | January | 06/01/2025. | 10.31am | 1 | Phone call | Upper Lachlan Shire | Speed limits | Unavoidable | Stakeholder phoned the HumeLink East delivery partner to request speed limits be reduced to 40km/hr along Prices Lane as the stakeholder is concerned when small children are visiting. | The HumeLink East delivery partner will investigate temporary actions to reduce speeds for its vehicles, if possible. Noting, that the delivery partner nor Transgrid are the regulatory authority for changing speed limits. This power lies with Transport for NSW in conjunction with local councils. The HumeLink East delivery partner will raise reduced speeds in project team meetings and with their subcontractors. The HumeLink East delivery partner will ensure the stakeholder is informed when project vehicles will be using the road more frequently. | TBC | Email sent to stakeholder 06/01/2025 | Closed | 06/01/2025.
2026 | January | 8/1/2026. | 10.48am | 1 | Phone call | Upper Lachlan Shire | Dust | Unavoidable | Stakeholder emailed the HumeLink East delivery partner and advised that project trucks are causing dust from the road to impact their home. | The HumeLink East delivery partner has been able divert project vehicles from the section of road near the stakeholder's property. The stakeholder was happy with that outcome. The HumeLink East delivery partner will discuss with its subcontractors around slowing their speed to reduce dust on Link Road. If the section of road is again used by the project, the HumeLink East delivery partner will water the road, when dry, to minimise dust. | ACT-136899 | Phone call made to stakeholder 08/01/2026. | Closed | 08/01/2026.
2026 | January | 16/01/2026 | 9.42am | 1 | Phone call | Snowy Valleys | Driving onto property | Avoidable | The HumeLink East delivery partner and the HumeLink West delivery partner received this and both investigated the claim | The HumeLink project delivery partners and there contractors were not conducting work at the time. The subsequent investigation identified that it was another project being undertaken. The HumeLink East delivery partner spoke with the concrete batch plant personnel who identified that the driver was one of their people. They would advise their drivers accordingly. | TBC | Phone call | Closed | 16/01/2026.
2026 | January | 19/01/2026. | 8.15am | 1 | Phone call | Upper Lachlan Shire | Dust | Unavoidable | Stakeholder emailed the HumeLink East delivery partner and advised that project trucks are causing dust from the road to impact their home. | Transgrid received notification, via the landowner's lawyer, of an alleged tresspass by a HumeLink East vehicle onto a landowner property. | TBC | Email | Closed | 2026-01-21
2026 | January | 19/01/2026. | 1.03pm | 1 | Phone call | Upper Lachlan Shire | Vehicle movements - using incorrect road | Avoidable | Stakeholder called to advise that the HumeLink East Delivery partner's heavy vehicles were coming down the wrong section of Greendale Road and Rye Park Road and that vehicles were doing three point turns in her driveway because the council had not maintained the section of road which turns into a swamp. Stakeholder advised that project should not use Google Maps as it was incorrect. | The HumeLink East delivery partner called the Stakeholder and will inspect the driveway to see if repairs are required and will provide advice in the internal daily meeting about the correct road directions. Stakeholder was happy with outcome. | ACT-135679 | Community phone called Phone call made to stakeholder | Closed | 21/01/2026.
2026 | January | 20/01/2026. | 12.28pm | 1 | Phone call | Upper Lachlan Shire | Road work - causing dust | Unavoidable | Stakeholder phoned the HumeLink East delivery partner to raise concerns around the condition of Stinkpot Road. |  | ACT-137787 | Phone call made to stakeholder Face to face meeting | Closed | 21/01/2026.
2026 | January | 21/01/2026. | 7.40 am | 1 | Phone call | Upper Lachlan Shire | Dust | Unavoidable | Stakeholder called directly to a HumeLink East delivery partner's mobile to advise that the amount of dust created was not satisfactory and they had not seen any water carts on Flacknell Creek Road and wanted something done about putting something down on the road. | The HumeLink East deliver partner advised stakeholder they would discuss with the construction team to have more water carts sent to the road. The HumeLink East delivery partner reviewed the roads in the area and will be undertaking the following activities. More water carts will service the road. As stated previously, the HumeLink East delivery partner is exploring options for longer lasting solutions and is monitoring recent placement of polymer to see its effectiveness. The HumeLink East delivery partner committed to calling stakeholder back to advise what was being done and advised that more water carts were going be allocated to the area. | ACT-136545 | Phone call made Email sent Phone call made | Closed | 21/01/2026.
2026 | January | 14/01/2026 | 12.17 pm | 1 | SMS | Upper Lachlan Shire | Dust - damage to driveway | Unavoidable | Stakeholder raised concerns regarding dust and the number of project vehicles using Loop Road. The stakeholder also advised they believed the project had damaged their driveway and wanted it repaired. | The HumeLink East delivery partner has responded to the stakeholder advising their process for investigation of damage and has directed their project vehicles to not use Loop Road. The HumeLink East delivery partner will review its records. The HumeLink East delivery partner could confirm one the video evidence was provided by the stakeholder that the vehicle was not a project vehicle but rather a council one. The Stakeholder will take their concerns up with Council. | ACT-136899 - connected to above - ongoing issue | Phone call, SMS, Email | Closed | 23/01/2026
2026 | January | 23/01/2026. | 11.45 am | 1 | Phone call | Upper Lachlan Shire | Gates being left open | Avoidable | Landowner called Transgrid complaining that the HumeLink East contractor has continually left gates open. | HumeLink East delivery partner will undertake internal investigation to understand what has been happening and provide advice to landowner. | ACT-136876 | Phone call | Open