## Complaints
Humelink East Project Complaints Register
Year | Month | Date | Time Received | Number of Complaints | How complaint was received | LGA | Topics Raised | Avoidable / Unavoidable | Summary | Responses and Investigation | Salesforce ID | Oustanding Actions | Status | Date Closed | Time Between Receipt of Compaint and Initial Response
2024 | November | 27/11/2024 | 12pm | 1 | Email | Yass Valley | Minor complaint - re: interactions with stakeholder | Avoidable | Received a complaint from from stakeholder about some interactions leading up to an event involving cultural activities and before the event. | Email sent with contact details to stakeholder Investigation was undertaken Phone call made to stakeholder Further discussions 13/12/2024 - Phone call and further emails Undertake lessons learnt Email out - 17 December 2024 recorded complaint | Activity number - ACT-88390 - ACT -89127 | None | Closed | 2024-09-12 | 24 hours
2024 | December | 2024-06-12 | AM | 1 | Text Message | Yass Valley | Participation on the project | Unavoidable | Stakeholder sent a text to complain about how they felt they werent included in the procurement process for the project. Advised they do not live on country anymore but felt they should still be able to be a representative working on the project. | Response: Phone call 6/12 at 3pm. emailed stakeholder - advised they could participate on the project will record complaint response sent - 9/12/2024 - expression of interest form was sent to stakeholder | Activity number ACT-89130 | None | Closed | 2024-09-12 | <6 hours
2025 | January | 2025-01-31 | AM | 1 | Phone call | Yass Valley | Property Management Plan meeting | Avoidable | Landowner called Transgrid complaining that the HumeLink East contractor rejected the request by the landowner for the Transgrid Landowner Access Officer to attend a meeting with the contractor and landowner to discuss the Property Management Plan. | ~ Landowner called Transgrid Landowner Access Officer on 31/1/2025 at 9:30am ~ Complaint recorded Contact landowner to confirm that Transgrid Landowner Access Officer will attend PMP meeting with contractor. | Activity number: ACT-92451 | None | Closed |  | <2Hours
2025 | February | 2025-02-06 | 11:24am | 1 | Phone call | Cootamundra/Gundagai | Road being damaged by trucks entering compound | Unavoidable | HumeLink East Place Manager (and Interface Manager in a separate call) received a call from a Cootamundra-Gundagai Regional council member about concerns raised by a local resident to the Council regarding road damage from trucks entering and leaving the new site compound in Adjungbilly. | HumeLink East Place Manager advised the council member that the HumeLink East team would investigate. Note that a pre-condition survey of this location has been completed prior to works. The project team inspected the site and confirmed no change in condition of the road, compared to the pre-condition survey. Documented in photographs. The project team has provided an update to the council member who shared the complaint. Project team to follow up with Council to check whether the resident would like a call to discuss. The project team will continue to monitor the condition of the road as there will be further heavy vehicle movements. An ongoing maintenance regime will be implemented ensuring any critical safety issues are addressed in a timely manner. Upon completion of the works in the area, a post-construction condition survey will be undertaken and any remedial works identified in consultation with the council will be completed. | Activity Number - ACT - 95585 | None | Closed | 2025-02-06 | <24hrs
2025 | February | 2025-02-12 | 9.17am | 1 | Email | Yass Valley | Poor driving behaviour of a HumeLink East member of staff driving a Company vehicle. | Avoidable | The community member advised by email that they were tailgated by a HumeLink East branded vehicle in a school zone in Yass at the end of drop-off time on this day. The driver then turned in front of a learner driver at traffic lights where the learner had right of way. | A HumeLink East Place Manager has contacted the community member by phone. Confirmed that poor driving behaviour is not tolerated, and HumeLink East would raise this in the pre-starts and toolbox talks to occur prior to work this week. The General Superintendent for HumeLink East was also called and the incident reported to him so this can be raised in pre-starts and toolboxes and code of driving conducted reiterated. The community member was unsure of the vehicle's number. The community member was satisfied by the project's swift response and actions of the project. Incident raised in pre-starts and toolboxes and code of driving conducted reiterated. HumeLink East sought to identify the driver and vehicle through HumeLink East vehicle tracking software. However, the vehicle could not be identified as the time of event could not be determined excatly. | Activity Number ACT-94176 | None | Closed | 2025-02-12 | <2Hours
2025 | March | 2025-03-24 | 1.06pm | 1 | Email | Upper Lachlan Shire | Gates left half open and latches not clipped | Avoidable | The Landowner emailed to advise the gates had been left half open and latches were not clipped on properly. There was a high risk of livestock getting out. | The Humelink Place Manager has contacted the Landowner by phone and discussed the issues raised. Advised the teams will be reminded again in pre-starts and tool box talks prior to work each day. This has been raised to senior management. The landowner was understanding and advised that it is very important that gates are left as found and any latches should be checked to make sure they are closed correctly. | Activity number ACT- 97316 | None | Closed | 24/3/2025 | 3 Hours
2025 | March | 2025-03-11 | 10am | 1 | Email | Upper Lachlan Shire | HumeLink East supervisor and contractor drove onto a landowner's property, unauthorised and unannounced, and had not adhered to agreed biosecurity practices. | Avoidable | Complaint came through Transgrid from the Australian Energy Infrastructure Commissioner on 27 March 2025. The landowner has requested an apology. The HumeLink East supervisor and contractor went onto the wrong property as they were given an incorrect address. Upon learning of the error, the supervisor apologised to the landowner. | This occurrence resulted from an inadvertent error involving an incorrect address supplied to the HumeLink East supervisor. When informed of the error by the landowner, the supervisor immediately apologised. HumeLink East has taken this matter seriously, conducted a thorough review of their processes, and implemented the necessary changes to avoid a similar incident in the future. Transgrid has written to the landowner, apologising for this incident. | Activity number - ACT 97761 | None | Closed | 2025-04-01 | <2Hours
2025 | March | 2025-03-25 | 10.24am | 1 | Email | Yass Valley | Transgrid transmission easement and access track property acquisition process | Unavoidable | The landowners have contacted EWON. Their claims about Transgrid include: providing misleading information, lack of engagement, delay tactics, incomplete ecology survey on the property, refusal to alter the alignment across a neighbouring property. The landowners say they have suggested an alternative alignment option which would avoid sensitive locations on their property, | Transgrid has been engaging with the landowners since 2020 and most recently had been investigating alternative transmission line alignment and access track locations on the landowners' property. Transgrid has been instructed not to contact the landowners further at this stage and to provide information for a resolution. Response to EWON sent on 04/04/2025. EWON requested further information. Response sent to EWON on15/04/2025. | Activity number - ACT 98433 | None | Closed | 2025-05-02 | <2Hours
2025 | April | 2025-04-04 | 12.22pm | 1 | Phone call | Sydney | Availability of RAP work on the project; concern around the allocation of work for the project; concern that they had not been selected to work on the project | Unavoidable | The complainant runs a business which responded to a tender to provide RAP services but has to date not been selected to do this work. HumeLink East has had an initial meeting with the sub-contractor that is engaged to coordinate those RAP businesses on the project. HumeLink East has returned the call of the complainant to advise it is investigating their concerns. The complainant was unhappy with this call. | HumeLink East is seeking further advice from the RAP sub-contractor regarding the tender response from this business. HumeLink East will review all infomation when provided so as to understand a better way to provide further transparency around RAP allocation processes. HumeLink East has committed to the complainant to contact them again on 07/04/2025 with an update on the investigation. HumeLink East has responded via email (07/04/2025) to this business addressing their concerns around work allocation and the process involved. The matter has been discussed with the RAP sub-contractor. HumeLink East included the project's complaints process in the response. | Activity number - ACT-98910 | None | Closed | 2025-04-07 | <2Hours
2025 | May | 2025-05-23 | 4.25pm | 1 | Letter | Snowy Valleys | Poor consultation and engagement with the Bryants. Request for reimbursement for legal costs. | Unavoidable | The complainant has been disappointed with the lack of engagement from the Project on any level of detail or impact to them. They have been away for extended periods of time over the last 18 months and are not aware of the impact of the project on them. Specifically, they highlighted: The only correspondence they have received has been legal in nature; the transmission lines visually impact their property and this will affect the value of their property; they wish to be reimbursed for legal costs that they have incurred; and the project has caused them concern and worry. | Legal expenses will be reimbursed by Transgrid. Required information will be requested from the complainant. | Activity number - ACT-103915 | Respond to community member by 3 June | Open |  | <2Hours